## General
Audit Recommendations Monitor
2025-10-31
Report / Action | Recommendation | Action Owner | Grade | Original timescale | Status at July 2025 | Status at October 2025 | Expected Completion Date | South Lanarkshire College management update as at 31 July 2025 | Evidence Supplied
2021/22
Cyber Security 2022-03 R9 | The Incident Response Process, and supporting playbooks, should be tested by way of a scenario-based desktop exercise to ensure staff know how to respond during an incident, and to also highlight any problem areas in the planned response. | Head of Digital and Governance Professional | 2 | 2023-03-31 | Fully implemented | Complete | 2025-11-30 | Incident response documents exist along with playbooks. Will need review and updated. Due to the changes in SLT staff following the restructure, it makes sense to move this back to later in the year or next session. Realistically it could be Sept 2025 before completion. Nov 25. Completed, the incident response training has been completed and we have a second planned for March. This will now be at minimum of once a year possibly twice a year based on the staff requiring the training. SLT at least once a year, a team or group as the second incident response at least once a year. | Evidence can be supplied in the form of the powerpoint and training materials. Will forward this to HL.
Health & Safety | We recommend the reporting of an Annual Health and Safety Report be incorporated into the forward workplan for the Human Resources Committee to ensure that Board Members have the opportunity to consider and approve the annual report and the forward workplan for health and safety activity for the coming year. | Head of People Services (previously Head of Facilities) | 3 | 2022-12-31 | Partially complete | Complete | 2025-11-30 | An annual report will be produced reporting on what has been completed during the year and set out the priorities and targets for the coming year. Staff absence has caused a delay in this piece of work progressing more fully but it will be carried out imminently for review at a future HR Committtee.(CF) Nov 25. Report produced and finalised. Being presented to the People & Culture Committee on 27th November 2025.
2022/23
Staff Recruitment & Retention 2023-03 R1 | It is recommended that the College define timeframes for completion of the ongoing review of its recruitment and selection policies to ensure that these are completed in a timely manner and are issued to the relevant staff for their understanding. | Head of People Services | 2 | 2024-01-20 | Partially complete | Partially complete | 2025-12-31 | Due to capacity issues within the HR team, the development of the policy has been delayed. The Policy is now in draft form and is currently going through an internal HR review before moving to the Senior Leadership Team, the Joint Negotiation Committee, the HR Committee and then the Board of Management. Nov 25. Recruitment Policy has been spproved by the Senior Leadership Team, Joint Negotiating Committee and is in the papers for the upcoming People & Culture Committee on 27th November 2025.
Staff Recruitment & Retention 2023-03 R2 | It is recommended that the College prepare procedural documents to formally document the administration processes to be followed when recruiting a new member of staff, to ensure that the process can be consistently performed by anyone in the event of staff absences / unexpected turnover. | Head of People Services | 3 | 2024-05-20 | In progress | In progress | 2025-12-31 | There has been delays with the role out of iTrent features, including the Recruitment module. The priority has been in ensuring payroll and pensions accuracy. Employee Self-Service has now been rolled out, and the College is seeking to implement the recruitment module during the first half of the next academic year. In saying that, the module is already well developed and partially tested. Nov 25. Recruitment Module on iTrent will likely be launched in December 2025 or January 2026, once the final adjustments are made to the system. Following this, a procedure will be communicated.
Staff Recruitment & Retention 2023-03 R5 | It is recommended that the College set out a clear timeline for importing all relevant hard copy documentation to the new HR system iTrent, to ensure that this data transfer is completed in a timely manner and to avoid a protracted scenario where some information is held electronically and some information is still held in hardcopy files | Head of People Services | 3 | 2024-05-20 | In progress | In progress | 2026-05-31 | The new HR & Payroll system is not fully in place yet. It is envisaged that a subsequent project to upload hard-copy documentation will follow this and will likely commence around December 2025 Nov 25. iTrent is still currently being developed. A plan for this is unlikely to commence until April or May 2026.
Budgetary Control 2023-04 R1 | The College should develop a formal budget setting timetable, setting out all key activities in the budget setting process from end to end, to ensure that all activities are completed timeously. The timetable may also assign tasks to responsible individuals, with target completion dates aligned with the Finance and Resources Committee meeting as appropriate. | Head of Finance | 3 | 2024-01-31 | In progress | In progress | 2026-05-01 | Budget Preparation guidance document prepared, which builds out the intended timeline for budget setting in accordance with the wider curriculum planning exercise. Alongside the Budget Prep guide, Finance are developing a GANTT chart to formalise the timetable.
Budgetary Control 2023-04 R2 | The College should consider developing enhanced real time financial information and dashboards, perhaps via Power BI, to allow Budget Holders to monitor actual income and expenditure against budget in real time. | Head of Finance | 3 | 2024-02-29 | In progress | In progress | 2026-05-01 | Work has been undertaken to develop a monthly management account pack, which will give enhanced information to budget holders. This will include area specific actual vs budget data, with two-way commentary. Expected rollout of this pack is Oct25 management accounts. Nov 25. Introductory meeting between VP and Symmetry to consider resource to enhance ReportPro implemantation. Once project is complete, users should have real-time account information.
Budgetary Control 2023-04 R3 | The Finance team should document the month end process currently followed by Finance, including preparation of budgeting information to allow for prompt publication of income and expenditure by budget line for review and monitoring by Budget Holders. This should be adapted as the capabilities of BluQube are enhanced to include generation of reports immediately following the completion of the month end close process to provide timely information. | Head of Finance | 3 | 2024-03-31 | In progress | In progress | 2026-05-01 | Finance use a checklist to complete the monthly management accounts. There are plans to replace the current management account pack to enhance the process. There are also plans to enhance BluQube to include budget information, to allow for a better user experience. These conversations have now begun, with a view to completing the process of enhancing BluQube / ReportPro data to allow for real time information. Once actioned, Finance will produce process notes to detail the Month End process.
Budgetary Control 2023-04 R4 | The College should develop a formal training programme for Budget Holders, which they are required to complete before they undertake their budget monitoring role. Detailed written procedures and guidance documents should also be developed (in parallel with the development of this tailored training for Budget Holders). This will provide a useful reference document for all Budget Holders, which they can consult, as required, following the training. | Head of Finance | 3 | 2024-05-31 | In progress | In progress | 2026-05-01 | A formal training programme has yet to be put in place but allowing for time to embed the Bluqube reporting package and have it fully operational, the College would expect to roll out training to budget holders in conjunction with new reporting system capabilities in 25/26. Nov 25. Although progress had been hampered by the restructure, the relevant users are now in post. Once ReportPro is fully up to date, work can begin to train users on the process. Budget process set for 2025/26, so focus will be on the next financial year.
Student Support Funds 2024-08 R1 | The College should ensure that distribution lists identifying Bursary students in receipt of study materials are maintained for each purchase invoice charged to the Bursary fund. Based on the current approach, the College should ensure that the planned study costs for each course still reflect the specific items or materials needed for the course and the current price from suppliers. | Management Accountant | 3 | 2024-02-29 | In progress | In progress | 2026-09-30 | The College will continue to analyse all study costs monthly and reconcile them back to Cost of Course forms, adjusting the Teqios system where required, and reconciling this to the general ledger. With regards to distribution lists, the College has implemented a document during the monthly reconciliation process that lists all bursary students and their course code/spend available however this did not tie in to actual spend. The College therefore accepts the action required now to attach actual spend to this document and will work with the curriculum managers to see if a better record of study cost spend can be kept at class level. The College commits to resolving this over the summer with a view to it being evidenced and confirmed in the next FES return audit in Sep 25. Initiated the set-up of study kit lists in similar format to those used by Hairdressing dept for each dept.
Student Support Funds 2024-08 R4 | Ensure that a check is made on the categorisation of ASN costs to ensure that they are correctly disclosed on the FES return. | Management Accountant | 3 | 2024-02-29 | In progress | In progress | 2026-09-30 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return. Unable to receive a monthly FES to check due to time constraints of other departments. Work to be done between MIS and Finance to ensure ability to check the data.
2023/24
Publicity & Communications | Crisis communication training should be delivered for the Principalship and the Marketing and Communications Manager. | Exec Team | 3 | 2024-07-31 | In progress | In progress | 2026-03-31 | The Principal and Vice-Principal - Student Experience and Innovation are comfortable with the level of training they have received to date. The Vice Principal - Finance, Resources & Sustainability and the Marketing and Communications Manager will undertake Media/Crisis Training with CDN. The training is scheduled for 24th March 2026.
Procurement & Creditors/Purchasing 2024-03 R1 | It is recommended that consideration be given to amending the approvals of low value purchase orders in PECOS to Vice Principals and Associate Principals (rather than requiring sign off by the Principal), to reduce the risk of a bottleneck. | Head of Finance | 3 | 2024-06-30 | In progress | In progress | 2026-03-31 | Given the ongoing College restructure and work that will be required to change the system parameters for new authorisations, this task has been delayed until a new College structure has been finalised to avoid unnecessary rework. Progress made. Procurement thresholds to be taken to board for approval, and implementation will occur thereafter.
Student Activity (Credits) 2024-07 R1 | Allocation of Credits to Courses For all College devised units, the College should ensure that adequate supporting evidence is available for planned learning hours to verify the Credits claim. | Head of Digital | 3 | Sep-25 | Partially complete | Complete | 2025-10-31 | College Units or “Non-SQA” units are a frequent issue. While I agree with the recommendation to get better at reporting the evidence, the college uses far fewer non-SQA units in their courses than previous years. That said, the timetabling and attendance for these modules needs improved using our current timetabling system. We will monitor this more closely with he timetabled hours vs actual hours power reporting as this was invaluable in the audit. At curriculum planning process, the CM’s will be challenged for using the non-SQA units, preventing unnecessary use of units in the courses. Record of work evidence is a lot clearer this year and can be used as supportive evidence for these modules. Nov 25. The recent credit audit for 24/25 has confirmed that this is now closed and fully implemented. Evidence has been provided as part of the credit audit. | Evidence provided as part of the credit audit
Student Activity (Credits) 2024-07 R2 2025-10 R2 | Required Dates and Attendance Ensure that the required dates for programmes and students recorded on the FES1 and FES2, respectively, are calculated in line with the Credits guidance. New critiera for this audit recommendation: For courses of 20 weeks or less, the required date should be calculated based on the date 25% of the length of the course has lapsed. | Head of Digital | 3 | Sep-25 | Partially complete | Partially complete | 2026-04-30 | Required date issues was not an issue at course level but it was at student level if the student finished early. The power bi report we use for checking the required date has been modified so we can see the student required date might be incorrect and reviewed at each FES quarter returns. The report was updated and being reviewed by the staff. However, there is a question around the validity of moving a required date that we need to speak to the auditors about as it changes the way SFC view the required date. (CS to follow up with HL) Nov 25. This has been partitially implemented and the original recommendation has been completed, however there is a specific issue around the course being 20 weeks or less where we have had a modification to the mode of attendance. This issue should be resolved by the move to unit-e but CS has requested that HL review this in-year rather than the next credit audit in Sept 26.
Student Support Funds 2024-08 R2 | The College should ensure that expenditure is correctly categorised on the study costs spreadsheet to allow a more accurate comparison of planned and actual expenditure. | Management Accountant | 3 | Dec 24 | In progress | In progress | 2026-02-28 | The cost of course forms will be updated to show a more realistic split of bursary spend for each department, departments that have ‘other’ as a category of spend with no history of any actual spend within this category will have this amount spread over the other categories based on likely spend. Invoices that have a number of different categories of bursary spend will be allocated accordingly. Update - This work will tie in with the development of the study kit lists to get a better idea of what each course will likely spend on each category. Cost of course forms will be tailored to match the study kit lists.
Student Support Funds 2024-08 R3 | The College should review student Award Assessment categorisation on the FES and ensure that any apparent misstatements are fully investigated and resolved | Management Accountant | 3 | Dec 24 | In progress | In progress | 2026-02-28 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return. Unable to receive a monthly FES to check due to time constraints of other departments. Work to be done between MIS and Finance to ensure ability to check the data.
Businss Process Review Space Management/Room Utilisation | The College's Estate Strategy needs to be updated to reflect the current space requirements of the curriculum, staff, and students. | Vice President - Finance, Resources & Sustainability | N/A | 2024-11-30 | In progress | In progress | 2026-03-31 | The existing Estates Strategy is very outdated but an update has started and will be progressed. Date extended out to allow time to carry out review.
Businss Process Review Space Management/Room Utilisation | A centralised room booking system is required that is visible by the whole College. | Head of Digital and Head of Facilities | N/A | 2025-08-31 | In progress | In progress | 2026-09-30 | The College agrees that there needs to be timetabling protocols and a room booking system that is visible and can be used by the whole College. This then allows for room utilisation data to be monitored. New access control system approved. Project set to be implented imminently, so further progress can be scheduled thereafter. Nov 25. The procurement of the new access control system has taken longer than expected, work is due to complete by the summer of 26. Therefore very little progres on this at the moment until the equipment is installed. Updated Completion date to Aug 2026.
Businss Process Review Space Management/Room Utilisation | Space management objectives and room utilisation targets need to be clearly defined in policies and procedures, accompanied by a structured space utilisation monitoring process. | Head of Curriculum, Head of Digital and Head of Facilities | N/A | 2025-12-23 | In progress | In progress | 2026-05-31 | Management agrees that policies and procedures (timetabling protocols and room booking) should be developed for cross college use. This is to be led by the curriculum area to enable support function departments to have systems in place. Nov 25. This is in progress along side the SFC infrastructure reporting. A revamp of the estates strategy is currently on-going and there has been progress on the room utlisation from the curriculum reporting. Progress on this will improve as we move into the new year and the power bi dashboards will begin to show the room utlisation more accurately. We also have established a timetable working group which will meet before christmas and their remit is to overhaul the timetable process.
2024/25
Payroll and Pensions Management | Review the capability within its Payroll team to prepare and submit the SPF member data for College employees in a timely and accurate manner. The College should consider strengthening the review and approval controls in place in relation to the data being submitted to the pension scheme administrators to minimise the risk of errors and subsequent inefficiencies in resolving SPFO’s and employees’ queries. The College should ensure that it is actively monitoring and enforcing the submission of accurate member data to ensure that the scenario where member data is out of date by several months does not reoccur. | Head of People Services | N/A | 2025-05-31 | Complete | Complete | 2025-05-31 | Completed
Payroll and Pensions Management | The College should ensure that multiple employees, across both Payroll and HR departments, have access to e-mail inboxes where queries can be received from pension scheme members in relation to the College’s management of their pension data. This is especially important due to the high risk of errors and misalignment between data held by the College and the pension scheme administrators, as demonstrated throughout our review. | Head of People Services | N/A | 2025-08-31 | In progress | Complete | 2025-07-31 | Completed Nov 25. The team are using a Helpdesk with this email address
Payroll and Pensions Management | The College should conduct a post-implementation review to provide confirmation that the new Payroll / HR system – iTrent – is configured in a way that provides adequate functionality for the management of employee pension data and allows the accurate, timely and efficient submission of required information to the pension scheme administrators. | Head of People Services | N/A | 2025-05-31 | In progress | Complete | 2025-12-31 | Nov 25. This check now forms part of the monthly payroll process.
Payroll and Pensions Management | The College should ensure that the new Payroll / HR system – iTrent – is configured in a way that offers adequate functionalities for managing employee pension data and assisting in accurately and efficiently submitting it to the pension scheme administrators. | Head of People Services | N/A | 2025-05-31 | In progress | In progress | 2026-08-31 | This is in progress; additional modules to be rolled out to enhance these functionalities Nov 25. The provider of iTrent are due to implement this functionality. No specific timeline is known yet.
Payroll and Pensions Management | Pension scheme members’ leaving status should be communicated to the relevant pension agency promptly, accurately, and in line with their requirements. The College should review its controls around managing employee data on its payroll system and ensure that any staff members are removed from it on their actual leaving date. It should be made impossible to pay staff members who have left the College through regular payroll payment runs. Monitoring controls should be introduced (potentially independent to the Payroll team) over the payroll payment runs to ensure that no ex-employees are included in payroll payment runs past the month in which they have left the organisation. | Head of People Services | N/A | 2025-04-30 | In progress | Complete | 2025-12-31 | Complete, with the exception of the reports being used as monitoring controls, which commence in April 2025 and likely be in place for Dec 2025 owing to ongoing work to devise appropriate monitoring reports in iTrent. Nov 25. This is in place
Payroll and Pensions Management | The College should ensure that adequate internal controls are in place to prevent and detect illegitimate payroll transactions, ex-employees being included within payroll processing, and errors. Risk-averse monitoring, review, and approval controls should be implemented (or strengthened) to ensure sufficient segregation of duties in processing the payroll. The capabilities of the new iTrent HR & payroll system should be leveraged to establish appropriate user access rights and embed approval controls within the process. | Head of People Services | N/A | 2025-04-30 | In progress | Complete | 2025-12-31 | Complete; certain illegitimate processes are impossible in the new system and approvals are in place for most aspect, Can be more widely demonstrated as further modules are rolled out.. Nov 25. The payroll controls prevent and detect any illegitimate transactions.
Payroll and Pensions Management | The College should consider undertaking a detailed exercise to determine how the historical overpayments to employees and pension schemes, as well as underpayments to HMRC, should be addressed and communicated to staff and other relevant stakeholders, including HMRC. The College should consider whether it has a complete view of instances where the ‘salary advance’ or other illegitimate adjustments were utilised and should take steps to determine whether these adjustments to HMRC payments are in any way connected to the fines levied by HMRC against the College in recent years | Head of People Services | N/A | 2025-07-31 | In progress | Complete | 2025-12-31 | Complete. Calculations and workings have been reviewed by HL, with a completion meeting taking place November 2025. Nov 25. This has been completed for Lecturing and Support Staff. Overcontributions have been returned to Lecturing staff, and will be returned to Support staff in the December 2025 payroll. The College is liaising with the Scottish Funding Council on a settlement where there has been undercontributions as an error of the College.
Payroll 2025-02 | The College should establish aprocedure for processing changes to employee standing data. This procedure should introduce a requirement that the staff member receiving and processing the request should independently confirm the request as genuine via a direct conversation with the relevant employee, for example by making a phone call and asking the employee to verify their new bank details (if the change relates to bank details). This should be carried out whether the request was received from a College email account or a non-College email account. A note to confirm that the change hasbeen verified directly with the relevant employee should be retained on file. Payroll Administrators, who are processing any requests for changes to employee standing data, should ensure that the source of the request to change employee data (such as a letter or email) is filed down appropriately, in order to provide an audit trail. | Head of People Services | 3 | 2025-05-31 | Complete | Complete | 2025-05-31 | Update- The College agreed the recommendation and put in place procedures for processing changes to employee standing data immediately. Nov 25. The College has enhanced the existing process to include checks with employees and the bank before proceeding.
Student Activity (Credits) 2025-10 R1 | Non fundable Activity R1 Ensure courses are assigned correct Source of Finance codes and checks are in place to confirm no Credits are claimed against programmes fully funded from non-SFC sources. | Head of Digital | 3 | N/A | n/a | Newly added | 2026-04-30 | This was due to the overall course setup in some areas where the master course may have had one type of source of finance and the class area had not been updated. This is a manual process and not easily noticed in the older systems. The initial test of the FES return from unit-e and credit claims shows that the credits are only added to the student based on the correct criteria for the source of finance so this issue, shouldn’t happen again. With many of these recommendations I would prefer to have an in-year check and confirmation with HL to confirm that the system is performing before the final return for 25/26 in October 2026
Student Activity (Credits) 2025-10 R3 | Classification of Programmes R3 Ensure that in-year data integrity checks include a review of Modes of Attendance, and other key data such as Credits claimed, to identify conflicts and that data is amended as required. | Head of Digital | 2 | N/A | n/a | Newly added | 2026-10-31 | The short full-time (SFT) courses have been the issue in this situation. There needs to a better strictness of the 18 weeks or less rule for the SFT course and not allowing CQM’s extending beyond that 18-week period. Extending the period forces the MIS staff to change this to a full-time mode of attendance. This is a process issue and needs checked at the curriculum planning process rather than the system side. Evidence of controls is difficult with this other than to display the check of all short full-time courses at the beginning of the year and then an in-year check to ensure the full-time and short full time courses match in terms of weeks on the system. To fully close this audit point, would only display in the final return in Sept/October 2026
Student Activity (Credits) 2025-10 R4 | Credit Values R4 Ensure that Credits claimed agree to the course framework or individual modules undertaken by students, based on SQA (or other awarding body) credit rating or planned learning hours/40. | Head of Digital | 3 | N/A | n/a | Newly added | 2026-10-31 | We already have a process known as “Credit matching” between the credits within the units and the claim against the student in the system. The improvement here would be have the credit match completed more regularly and ensure that the unit’s added are not modified excessively during the academic year. To fully close this audit point, would only display in the final return in Sept/October 2026