## General
Audit Recommendations Monitor
2026-01-01
Report / Action | Recommendation | Action Owner | Grade | Original timescale | Status at October 2025 | Status at January 2026 | Expected Completion Date | South Lanarkshire College management update as at 31 July 2025 | Evidence Supplied
Student Support Funds 2022-09 R2 | The College should undertake a review to identify digital study materials and determine a basis for apportioning costs to Bursary students, ensuring that the cost of any core teaching materials that should be covered by the core grant and any costs relating to non- Bursary students are excluded. | Management Accountant | 2 | 2023-03-31 | Partially complete | Partially complete | 2026-09-30 | The Head of Finance will work with the Management Accountant to identify an acceptable and relevant costing model for this recommendation, and ensure it is implemented fairly. There may be an input required from Head of Digital. The college will look to close out the recommendation by the end of September 26.
Student Support Funds 2024-08 R1 | The College should ensure that distribution lists identifying Bursary students in receipt of study materials are maintained for each purchase invoice charged to the Bursary fund. Based on the current approach, the College should ensure that the planned study costs for each course still reflect the specific items or materials needed for the course and the current price from suppliers. | Management Accountant | 3 | 2024-02-29 | In progress | In progress | 2026-09-30 | The College will continue to analyse all study costs monthly and reconcile them back to Cost of Course forms, adjusting the Teqios system where required, and reconciling this to the general ledger. With regards to distribution lists, the College has implemented a document during the monthly reconciliation process that lists all bursary students and their course code/spend available however this did not tie in to actual spend. The College therefore accepts the action required now to attach actual spend to this document and will work with the curriculum managers to see if a better record of study cost spend can be kept at class level. The College commits to resolving this over the summer with a view to it being evidenced and confirmed in the next FES return audit in Sep 25. Initiated the set-up of study kit lists in similar format to those used by Hairdressing dept for each dept.
Student Support Funds 2024-08 R2 | The College should ensure that expenditure is correctly categorised on the study costs spreadsheet to allow a more accurate comparison of planned and actual expenditure. | Management Accountant | 3 | Dec 24 | In progress | In progress | 2026-09-30 | The cost of course forms will be updated to show a more realistic split of bursary spend for each department, departments that have ‘other’ as a category of spend with no history of any actual spend within this category will have this amount spread over the other categories based on likely spend. Invoices that have a number of different categories of bursary spend will be allocated accordingly. This work will tie in with the development of the study kit lists to get a better idea of what each course will likely spend on each category. Cost of course forms will be tailored to match the study kit lists.
Student Support Funds 2024-08 R3 | The College should review student Award Assessment categorisation on the FES and ensure that any apparent misstatements are fully investigated and resolved | Management Accountant | 3 | Dec 24 | In progress | In progress | 2026-09-30 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return. Unable to receive a monthly FES to check due to time constraints of other departments. Work to be done between MIS and Finance to ensure ability to check the data.
Student Support Funds 2024-08 R4 | Ensure that a check is made on the categorisation of ASN costs to ensure that they are correctly disclosed on the FES return. | Management Accountant | 3 | 2024-02-29 | In progress | In progress | 2026-09-30 | The monthly categorisation check of FES categories will include a check of ASN costs to ensure that they are being disclosed correctly going forward. This is monitored from Aug - Jan then implemented from Feb - Jun once full quote of students are included on the FES return. Unable to receive a monthly FES to check due to time constraints of other departments. Work to be done between MIS and Finance to ensure ability to check the data.
Staff Recruitment & Retention 2023-03 R1 | It is recommended that the College define timeframes for completion of the ongoing review of its recruitment and selection policies to ensure that these are completed in a timely manner and are issued to the relevant staff for their understanding. | Head of People Services | 2 | 2024-01-20 | Partially complete | Completed, pending HL review of evidence | 2025-12-31 | Due to capacity issues within the HR team, the development of the policy has been delayed. The Policy is now in draft form and is currently going through an internal HR review before moving to the Senior Leadership Team, the Joint Negotiation Committee, the HR Committee and then the Board of Management. Nov 25. Recruitment Policy has been approved by the Senior Leadership Team, Joint Negotiating Committee and is in the papers for the upcoming People & Culture Committee on 27th November 2025. Jan 26: Policy approved at BoM in December 2025 | People Services to confirm they have sent over relevant documentation to Henderson Loggie on this recommendation.
Staff Recruitment & Retention 2023-03 R2 | It is recommended that the College prepare procedural documents to formally document the administration processes to be followed when recruiting a new member of staff, to ensure that the process can be consistently performed by anyone in the event of staff absences / unexpected turnover. | Head of People Services | 3 | 2024-05-20 | In progress | In progress | 2026-05-31 | Further to the audit recommendation regarding the preparation of procedural documents for the recruitment process, there has been a delay to the originally planned completion date. The delay has been primarily due to resource and capacity constraints, including team absence and a six-week pause in external system support while the College’s MHR consultant was on sick leave, during which no alternative consultant support was provided. As a result, planned configuration, testing and documentation activity for the iTrent Recruitment module was temporarily paused. The Recruitment module itself is well developed and partially tested, and rollout activity has now resumed. Implementation is now scheduled for March/April 2026, following which the recruitment procedures will be formally documented and communicated. These procedures will ensure recruitment administration processes are consistently applied and are resilient to staff absence or turnover.
Staff Recruitment & Retention 2023-03 R5 | It is recommended that the College set out a clear timeline for importing all relevant hard copy documentation to the new HR system iTrent, to ensure that this data transfer is completed in a timely manner and to avoid a protracted scenario where some information is held electronically and some information is still held in hardcopy files | Head of People Services | 3 | 2024-05-20 | In progress | In progress | 2026-05-31 | The new HR & Payroll system is not fully in place yet. It is envisaged that a subsequent project to upload hard-copy documentation will follow this and will likely commence around December 2025 Nov 25. iTrent is still currently being developed. Jan 26: Work is still ongoing, with the expected completion date May 2026.
Staff Recruitment & Retention 2023-03 R6 | It is recommended that the College implement ongoing engagement measures to capture levels of staff satisfaction to reduce the risk of employees leaving the employment of the College due to issues which could have been managed and resolved had they been identified earlier. | Head of People Services | 3 | 2025-11-20 | In progress | In progress | 2026-05-31 | An employee engagement framework has been researched, developed and implemented. Initial baseline measures have taken place to assess the current status of engagement. Further activities will take place during the 2025-26 Academic. Year to refine a process for assessment, measuring and responding to employee satisfaction and engagement.
Budgetary Control 2023-04 R1 | The College should develop a formal budget setting timetable, setting out all key activities in the budget setting process from end to end, to ensure that all activities are completed timeously. The timetable may also assign tasks to responsible individuals, with target completion dates aligned with the Finance and Resources Committee meeting as appropriate. | Head of Finance | 3 | 2024-01-31 | In progress | In progress | 2026-05-31 | Budget Preparation guidance document prepared, which builds out the intended timeline for budget setting in accordance with the wider curriculum planning exercise. Alongside the Budget Prep guide, Finance are developing a GANTT chart to formalise the timetable. Finance have recruited a temporary Financial Accountant who will work with the Management Accountant and the Head of Finance to finalise the Budget Setting process before work begins on the 2026-27 budget.
Budgetary Control 2023-04 R2 | The College should consider developing enhanced real time financial information and dashboards, perhaps via Power BI, to allow Budget Holders to monitor actual income and expenditure against budget in real time. | Head of Finance | 3 | 2024-02-29 | In progress | In progress | 2026-05-01 | Work has been undertaken to develop a monthly management account pack, which will give enhanced information to budget holders. Introductory meeting between VP and Symmetry to consider resource to enhance ReportPro implemantation. Once project is complete, users should have real-time account information. Jan26 New Management Account presented to SLT in January. This will be enhanced for February rollout of the January accounts to budget holders.
Budgetary Control 2023-04 R3 | The Finance team should document the month end process currently followed by Finance, including preparation of budgeting information to allow for prompt publication of income and expenditure by budget line for review and monitoring by Budget Holders. This should be adapted as the capabilities of BluQube are enhanced to include generation of reports immediately following the completion of the month end close process to provide timely information. | Head of Finance | 3 | 2024-03-31 | In progress | In progress | 2026-05-01 | Finance use a checklist to complete the monthly management accounts. The management account pack has now been enhanced. There are also plans to enhance BluQube to include budget information, to allow for a better user experience. These conversations have now begun, with a view to completing the process of enhancing BluQube / ReportPro data to allow for real time information. Once actioned, Finance will produce process notes to detail the Month End process.
Budgetary Control 2023-04 R4 | The College should develop a formal training programme for Budget Holders, which they are required to complete before they undertake their budget monitoring role. Detailed written procedures and guidance documents should also be developed (in parallel with the development of this tailored training for Budget Holders). This will provide a useful reference document for all Budget Holders, which they can consult, as required, following the training. | Head of Finance | 3 | 2024-05-31 | In progress | In progress | 2026-05-01 | A formal training programme has yet to be put in place but allowing for time to embed the Bluqube reporting package and have it fully operational, the College would expect to roll out training to budget holders in conjunction with new reporting system capabilities in 25/26. Although progress had been hampered by the restructure, the relevant users are now in post. Once ReportPro is functional, work can begin to train users. The budget is already set for 2025/26, so focus will be on the next financial year.
Publicity & Communications 2024-02 R2 | Crisis communication training should be delivered for the Principalship and the Marketing and Communications Manager. | Exec Team | 3 | 2024-07-31 | In progress | In progress | 2026-03-31 | The Principal and Vice-Principal - Student Experience and Innovation are comfortable with the level of training they have received to date. The Vice Principal - Finance, Resources & Sustainability and the Marketing and Communications Manager will undertake Media/Crisis Training with CDN. The training is scheduled for 24th March 2026.
Procurement & Creditors/Purchasing 2024-03 R1 | It is recommended that consideration be given to amending the approvals of low value purchase orders in PECOS to Vice Principals and Associate Principals (rather than requiring sign off by the Principal), to reduce the risk of a bottleneck. | Head of Finance | 3 | 2024-06-30 | In progress | In progress | 2026-03-31 | Given the ongoing College restructure and work that will be required to change the system parameters for new authorisations, this task has been delayed until a new College structure has been finalised to avoid unnecessary rework. Progress made. Procurement thresholds and Finance Regulations to be updated to match, before being presented to SLT for confirmation.
Business Process Review Space Management/Room Utilisation 2024-05 R1 | A refresh of the College Estate Strategy is necessary to address the evolving needs of all estate users. This should be based on a thorough review of space requirements for curriculum delivery, support staff (including workspaces and meeting rooms), and students (including social and selfstudy areas). The strategy should also explore how blended learning and hot desking practices could reduce the need for physical space. | Vice President - Finance, Resources & Sustainability | N/A | 2024-11-30 | In progress | In progress | 2026-03-31 | The existing Estates Strategy is very outdated but an update has started and will be progressed. Jan 26: The college has gone through the procurement process to engage a company to perform the review. Work commences on 26 February 2026
Business Process Review Space Management/Room Utilisation 2024-05 R2 | Develop space management policies and procedures that include optimal room utilisation targets (both in terms of frequency and occupancy) for specialised and general teaching areas. Implement a process to regularly review and audit room utilisation data, integrating information from attendance records, timetabling, and room occupancy sensors. This will help identify areas of over- or underutilisation, enabling better planning for alternative uses. | Head of Curriculum, Head of Digital and Head of Facilities | N/A | 2025-12-23 | In progress | In progress | 2026-05-31 | Management agrees that policies and procedures (timetabling protocols and room booking) should be developed for cross college use. This is to be led by the curriculum area to enable support function departments to have systems in place. This is in progress along side the SFC infrastructure reporting. A revamp of the estates strategy is currently on-going and there has been progress on the room utlisation from the curriculum reporting.
Business Process Review Space Management/Room Utilisation 2024-05 R3 | Management should consider implementing a Room Booking System that consolidates timetabling information and other rooms to provide information on real-time room availability, enabling staff to easily review and identify appropriate rooms. | Head of Digital and Head of Facilities | N/A | 2025-08-31 | In progress | In progress | 2026-09-30 | The College agrees that there needs to be timetabling protocols and a room booking system that is visible and can be used by the whole College. This then allows for room utilisation data to be monitored. New access control system approved. Project set to be implented imminently, so further progress can be scheduled thereafter. The procurement of the new access control system has taken longer than expected, work is due to complete by the summer of 26. Therefore very little progres on this at the moment until the equipment is installed. Updated Completion date to Aug 2026. Jan 26: The new student management system UnitE, contains a timetabling module. A timetabling group has been established to enable new timetabling protocols to be in place for the 2026-27 academic year. This will provide robust room utilisation data.
Student Activity 2024-07 R2 | Ensure that the required dates for programmes and students recorded on the FES1 and FES2, respectively, are calculated in line with the Credits guidance. | Head of Digital | 3 | N/A | Partially complete | Completed, pending HL review of evidence | 2026-04-30 | This has been reviewed, and the correct controls should now be in place. Henderson Loggie noted that there were issues noted with the calculation of required dates during our sample testing for 2024/25. | Digital to confirm they have sent over relevant documentation to Henderson Loggie on this recommendation.
Student Activity (Credits) 2025-10 R1 | Ensure courses are assigned correct Source of Finance codes and checks are in place to confirm no Credits are claimed against programmes fully funded from non-SFC sources. | Head of Digital | 3 | N/A | Newly added | In progress | 2026-04-30 | This was due to the overall course setup in some areas where the master course may have had one type of source of finance and the class area had not been updated. This is a manual process and not easily noticed in the older systems. The initial test of the FES return from unit-e and credit claims shows that the credits are only added to the student based on the correct criteria for the source of finance so this issue, shouldn’t happen again. With many of these recommendations MIS would prefer to have an in-year check and confirmation with HL to confirm that the system is performing before the final return for 25/26 in October 2026
Student Activity (Credits) 2025-10 R2 | For courses of 20 weeks or less, the required date should be calculated based on the date 25% of the length of the course has lapsed. | Head of Digital | 3 | Sep-25 | Partially complete | Partially complete | 2026-04-30 | This has been partially implemented and the original recommendation has been completed, however there is a specific issue around the course being 20 weeks or less where we have had a modification to the mode of attendance. This issue should be resolved by the move to unit-e but CS has requested that HL review this in-year rather than the next credit audit in Sept 26.
Student Activity (Credits) 2025-10 R3 | Ensure that in-year data integrity checks include a review of Modes of Attendance, and other key data such as Credits claimed, to identify conflicts and that data is amended as required. | Head of Digital | 2 | N/A | Newly added | In progress | 2026-10-31 | The short full-time (SFT) courses have been the issue in this situation. There needs to be improved enforcement of the 18 weeks or less rule for SFT courses, and CQMs cannot extend beyond that 18-week period once in the curriculum plan. Extending the period forces the MIS staff to change this to a full-time mode of attendance. This is a process issue and needs checked at the curriculum planning process rather than the system side. Evidence of controls is difficult with this other than to display the check of all short full-time courses at the beginning of the year and then an in-year check to ensure the full-time and short full time courses match in terms of weeks on the system. To fully close this audit point, would only display in the final return in Sept/October 2026. Jan 2026: The College will undertake in year "audit" or "census" checks to ensure alignment with curriculum plan.
Student Activity (Credits) 2025-10 R4 | Ensure that Credits claimed agree to the course framework or individual modules undertaken by students, based on SQA (or other awarding body) credit rating or planned learning hours/40. | Head of Digital | 3 | N/A | Newly added | In progress | 2026-10-31 | There is already a process known as “Credit matching” between the credits within the units and the claim against the student in the system. The improvement here would be ro have the credit match completed more regularly and ensure that the units added are not modified excessively during the academic year. To fully close this audit point, would only display in the final return in Sept/October 2026
Environmental Sustainability 2025-06 R1 | Management should update the CCAT remit and define key stakeholder groups that must attend, for example, the Strategic Lead, APUC / Supply Chain Manager, ICT, the Business Innovation Team, or HR, or those with partnership responsibilities. Meeting minutes should track attendance and apologies, to encourage attendance. | Head of Curriculum | 3 | 2026-06-30 | n/a | Newly added | 2026-06-30 | Agreed, relevant changes will be made post restructure and will be set out clearly by the Senior Leadership Team.
Environmental Sustainability 2025-06 R2 | Management should take steps to ensure that there is sufficient capacity within the Sustainability Officer role, particularly as key Net Zero deadlines approach. Additionally, CCEAP actions should be distributed more widely across the CCAT so to strengthen delivery and accountability. | Head of Facilities | 3 | 2026-03-31 | n/a | Completed, pending HL review of evidence | 2026-03-31 | Agreed, this post needs to be full time role to drive forward the actions required. Jan 26: Post has been filled. Recommendation will be reviewed as such, with further update in following quarter. | Facilities to confirm they have sent over relevant documentation to Henderson Loggie on this recommendation.
Environmental Sustainability 2025-06 R3 | The Environmental Sustainability Policy should either be updated, or related guidance created, to reference the GHG Protocol, clearly defining the College’s categories that define Scope 1, 2, and 3 emissions in order to ensure alignment with the GHG protocol. This may require discussion with other similar organisations to ensure consistency across the sector. | Head of Facilities | 3 | 2026-06-30 | n/a | Newly added | 2026-06-30 | Agreed, the college will focus on this.
Environmental Sustainability 2025-06 R4 | Management should consider developing a zero-tolandfill strategy with clearly defined commodity targets, actions (not just key commodities) and assigning ownership of actions within a waste management plan across key stakeholder groups, including staff and students. Consideration should be given to linking plans to performance indicators, such as performance achieved with waste contractors. | Head of Facilities | 3 | 2026-06-30 | n/a | Newly added | 2026-06-30 | Agreed, in recent months the landfill waste has decreased but is still high. There needs to be a joint working approach with curriculum, procurement and the waste contractors.
Building Maintenance 2025-08 R1 | It is recommended that the College develops its new Estates Strategy, which reflects the College’s financial landscape, student needs and physical condition, in a timely manner to ensure alignment with the wider College Strategy. | Vice President - Finance, Resources & Sustainability | 2 | 2026-07-31 | n/a | Newly added | 2026-07-31 | The College is currently considering a longer-term plan to renovate some areas of the Campus to better support both student and staff needs and expects to use the residual months of academic year 2025-2026 to engage consultancy support to help design a fit for purpose infrastructure plan that will underpin and help to shape a revision of the Estates strategy.
Building Maintenance 2025-08 R2 | Consideration should be given to scheduling condition surveys in the coming years to identify the areas of focus in line with the College’s strategic goals and the new Estates Strategy, once this is in place. | Head of Facilities | 3 | 2026-07-31 | n/a | Newly added | 2026-07-31 | The College will consider scheduling more routine condition surveys and will provide a timeline in 2026 for work to be undertaken in future years.
Building Maintenance 2025-08 R3 | Review the system for monitoring PPM to ensure that all is completed in line with the agreed PPM schedule and that evidence to confirm this is retained. | Head of Facilities | 3 | 2026-03-31 | n/a | Newly added | 2026-03-31 | The College has requested an update from the contractor as to why the 6 - monthly PPM check performed in April 2025 was only returned to the College in September 2025, with no recurring PPM check in October 2025 noted. This will be reported back to the contractor as part of its standard contract monitoring with improvements expected and a further PPM check to be initiated in place of the October 2025 check. Additionally, an enhancement of the PPM schedule as noted at R4 will better support monitoring and provide a means to evidence the completion of PPM works.
Building Maintenance 2025-08 R4 | It is recommended that the College formalises the specific times planned for each of the PPM works to ensure that these are accurately recorded, and that the costs of these works are clearly documented and understood prior to them being undertaken. | Head of Facilities | 3 | 2026-03-31 | n/a | Newly added | 2026-03-31 | The College is currently enhancing its PPM to include a lower level of detail, including specific timelines for PPMs and the costs associated with these works. Initially this will be retained and updated manually with the expectation that a Computer Aided Facilities Management (CAFM) system could be utilised in future years.
Payroll and Pensions Management | The College should ensure that the new Payroll / HR system – iTrent – is configured in a way that offers adequate functionalities for managing employee pension data and assisting in accurately and efficiently submitting it to the pension scheme administrators. | Head of People Services | N/A | 2025-05-31 | In progress | In progress | 2026-08-31 | This is in progress; additional modules to be rolled out to enhance these functionalities The provider of iTrent are due to implement this functionality. No specific timeline is known yet.
Note on I23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Is this now complete then? @Paddy Feechan Reply: @Elaine McKechnie Reply: Hi Stella, no, not entirely. I think all we need to do to complete this one is for Chris to evidence the findings to Henderson Loggie. HL included this as an open recommendation on the Follow-up Audit documentation. I'll take note to chase Chris to close this out officially with HL. Partially complete us the correct status at the moment.
Note on I29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can this be marked as completed? @Paddy Feechan @Elaine McKechnie Reply: Hi Stella, we won't be able to mark them as officially complete until the college sends on evidence to Henderson Loggie that the recommendation has been actioned, and then Henderson Loggie acknowledge this. This is why the below risk in I23 was put back on the monitor file. We were asked to remove it as it was complete, but Henderson Loggie never saw any evidence that it was, so continued to carry it as an open item. I can update the commentary to that effect, and chase Craig on this one to get evidence over to HL as soon as he can?