## SLC Summary
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2026-01-22
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2026-01-22
|  |  | Next date of review (Expected not actual) |  |  |  | 2026-04-30
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Oversight | Risk Appetite Category | Risk Appetite | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check! | Assurance Mapping | Assurance Mapping Source
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of Digital | VP - Finance, Resources & Sustainability | Information | Cautious | 6 | 3 | 0 | 0 | Internal | e.g access controls; data encryption, policies and procedures, physical security, data back up, compliance and penetration testing
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | Head of Finance | VP - Finance, Resources & Sustainability | Financial | Cautious | 20 | 20 | 0 | 0 | Internal & External | Internal e.g. financial planning and forecasting; monthly reporting; robust financial governance and risk management External e.g. Internal/External Audit
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 3 | 15 | 10 | 5 | Head of Finance Head of People Services | VP - Finance, Resources & Sustainability | Financial | Cautious | 15 | 15 | 0 | -5 | Internal & External | Internal e.g. Robust financial governance; effective policies and procedures, management assurances External e.g. Internal/External audit
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | Head of Curriculum Head of Digital | VP for Student Experience and Innovation | Financial | Cautious | 15 | 10 | 0 | 0 | Internal & External | Internal e.g. accurate data collection and monitoring; External e.g. Internal Audit/Scottish Funding Council
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 4 | 16 | 16 | 0 | 4 | 3 | 12 | 12 | 0 | Head of Finance Head of Facilities | VP - Finance, Resources & Sustainability | Financial | Cautious | 16 | 12 | 0 | 0 | Internal | Robust and frequent reporting of capital expenditure plans; regular cashflow monitoring
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 3 | 12 | 12 | 0 | 3 | 2 | 6 | 6 | 0 | Governance & Compliance Professional | Principal | Governance | Minimal | 12 | 6 | 0 | 0 | Internal & External | Internal e.g. experienced Governance Professional and robust Governance reporting and Compliance with the Code of Good Governance for Scottish FE colleges. External e.g. Board Effectiveness Reviews by Colleges Development Scotland
Health and Safety
6 | That there is a failure to meet statutory and legislative health and safety. | 2 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 15 | 10 | 5 | Head of People Services Head of Facilities | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Qualified Health & Safety Advisor in post; frequent reporting and evidence of quarterly Health & Safety committee meetings External e.g. Colleges Scotland, Scottish Funding Council and HSE Scotland
Legal/Compliance
4 | That there is a breach of legislation and associated regulations in relation to HR, Quality, Finance and GDPR | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of Digital Head of Finance Head of People Services Head of Facilities Head of Quality | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Robust governance; effective policies and procedures, management assurances External e.g. Internal/External Audit
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Head of Student Services Head of People Services | VP for Student Experience and Innovation | Legal/Compliance | Cautious | 9 | 3 | 0 | 0 | Internal & External | Internal e.g. Governance & oversight, effective policies and procedures, training and awareness External e.g. Internal Audit/Education Scotland
15 | That the College is not on track to meet the Scottish Government net zero sustainability priorities. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | Head of Facilities Head of Curriculum | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Governance & Oversight, effective policies and procedures, robust Strategy, internal collation and monitoring of carbon data External e.g. Internal Audit/Annual Public Body Climate Change Reporting PBCCR;
Operations
9 | That there is a failure to achieve high standards of learning and teaching and assessment. | 1,2 | 4 | 3 | 12 | 12 | 0 | 4 | 1 | 4 | 4 | 0 | Head of Curriculum | VP for Student Experience and Innovation | Operations | Open | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Governance oversight, performance monitoring External e.g. QAA Scotland/Teritiary Quality Enhancement Frameworks (TQEF)/Education Scotland/Scottish Funding Council/Professional Accreditation bodies/External Audit
12 | That the College cannot provide a robust learner experience supporting them onto positive destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | Head of Quality and Learning and Teaching Innovation | VP for Student Experience and Innovation | Operations | Open | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Governance & Oversight, staff training, continuous improvement External e.g. QAA Scotland/Tertiary Quality Enhancemeny Framework/Professional Accreditation
People | [19 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 4 | 16 | 16 | 0 | 4 | 2 | 8 | 8 | 0 | Head of People Services | Principal | People | Eager | 16 | 8 | 0 | 0 | Internal | Governance & Oversight, staff training, staff feedback, performance monitoring, external benchmarking , risk management and continuous improvement.
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 5 | 15 | 15 | 0 | 3 | 4 | 12 | 12 | 0 | Head of Digital | VP - Finance, Resources & Sustainability | Property | Minimal | 15 | 12 | 0 | 0 | Internal & External | Internal e.g. Business Continuity Planning; Governance & Oversight, effective communication plan and risk management. External e.g. Insurance Providers/ISO 22301 Certification
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 3 | 12 | 12 | 0 | 3 | 3 | 9 | 9 | 0 | All Heads of Department | Principal | Strategy | Open | 12 | 9 | 0 | 0 | Internal | Governance & Oversight, Policies and Codes of Conduct, effecrive crisis management and business; continuity, stakeholder engagmeent and effective communication
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability

## Nov 25 SLC Summary (hidden)
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2025-11-04
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2025-11-04
|  |  | Next date of review (Expected not actual) |  |  |  | 2026-01-22
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Oversight | Risk Appetite Category | Risk Appetite | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check! | Assurance Mapping | Assurance Mapping Source
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of Digital | VP - Finance, Resources & Sustainability | Information | Cautious | 6 | 3 | 0 | 0 | Internal | e.g access controls; data encryption, policies and procedures, physical security, data back up, compliance and penetration testing
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | Head of Finance | VP - Finance, Resources & Sustainability | Financial | Cautious | 20 | 20 | 0 | 0 | Internal & External | Internal e.g. financial planning and forecasting; monthly reporting; robust financial governance and risk management External e.g. Internal/External Audit
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | Head of Finance Head of People Services | VP - Finance, Resources & Sustainability | Financial | Cautious | 15 | 10 | 0 | 0 | Internal & External | Internal e.g. Robust financial governance; effective policies and procedures, management assurances External e.g. Internal/External audit
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 5 | 5 | Head of Curriculum Head of Digital | VP for Student Experience and Innovation | Financial | Cautious | 15 | 10 | 0 | -5 | Internal & External | Internal e.g. accurate data collection and monitoring; External e.g. Internal Audit/Scottish Funding Council
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 4 | 16 | 12 | 4 | 4 | 3 | 12 | 12 | 0 | Head of Finance Head of Facilities | VP - Finance, Resources & Sustainability | Financial | Cautious | 16 | 12 | -4 | 0 | Internal | Robust and frequent reporting of capital expenditure plans; regular cashflow monitoring
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 3 | 12 | 25 | -13 | 3 | 2 | 6 | 20 | -14 | Governance & Compliance Professional | Principal | Governance | Minimal | 12 | 6 | 13 | 14 | Internal & External | Internal e.g. experienced Governance Professional and robust Governance reporting and Compliance with the Code of Good Governance for Scottish FE colleges. External e.g. Board Effectiveness Reviews by Colleges Development Scotland
Health and Safety
6 | That there is a failure to meet statutory and legislative health and safety | 2 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | Head of People Services Head of Facilities | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Qualified Health & Safety Advisor in post; frequent reporting and evidence of quarterly Health & Safety committee meetings External e.g. Colleges Scotland, Scottish Funding Council and HSE Scotland
Legal/Compliance
4 | That there is a breach of legislation and associated regulations in relation to HR, Quality, Finance and GDPR | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of Digital Head of Finance Head of People Services Head of Facilities Head of Quality | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Robust governance; effective policies and procedures, management assurances External e.g. Internal/External Audit
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Head of Student Services Head of People Services | VP for Student Experience and Innovation | Legal/Compliance | Cautious | 9 | 3 | 0 | 0 | Internal & External | Internal e.g. Governance & oversight, effective policies and procedures, training and awareness External e.g. Internal Audit/Education Scotland
15 | That the College is not on track to meet the Scottish Government net zero sustainability priorities. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | Head of Facilities Head of Curriculum | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Governance & Oversight, effective policies and procedures, robust Strategy, internal collation and monitoring of carbon data External e.g. Internal Audit/Annual Public Body Climate Change Reporting PBCCR;
Operations
9 | That there is a failure to achieve high standards of learning, teaching and assessment. | 1,2 | 4 | 3 | 12 | 12 | 0 | 4 | 1 | 4 | 4 | 0 | Head of Curriculum | VP for Student Experience and Innovation | Operations | Open | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Governance oversight, performance monitoring External e.g. QAA Scotland/Teritiary Quality Enhancement Frameworks (TQEF)/Education Scotland/Scottish Funding Council/Professional Accreditation bodies/External Audit
12 | That the College cannot provide a robust learner experience supporting them onto their positive destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 12 | -8 | Head of Quality and Learning and Teaching Innovation | VP for Student Experience and Innovation | Operations | Open | #N/A | #N/A | #N/A | #N/A | Internal & External | Internal e.g. Governance & Oversight, staff training, continuous improvement External e.g. QAA Scotland/Tertiary Quality Enhancemeny Framework/Professional Accreditation
People | [19 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 4 | 16 | 8 | 8 | 4 | 2 | 8 | 16 | -8 | Head of People Services | Principal | People | Eager | 16 | 8 | -8 | 8 | Internal | Governance & Oversight, staff training, staff feedback, performance monitoring, external benchmarking , risk management and continuous improvement.
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 5 | 15 | 15 | 0 | 3 | 4 | 12 | 12 | 0 | Head of Digital | VP - Finance, Resources & Sustainability | Property | Minimal | 15 | 12 | 0 | 0 | Internal & External | Internal e.g. Business Continuity Planning; Governance & Oversight, effective communication plan and risk management. External e.g. Insurance Providers/ISO 22301 Certification
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 3 | 12 | 16 | -4 | 3 | 3 | 9 | 12 | -3 | All Heads of Department | Principal | Strategy | Open | 12 | 9 | 4 | 3 | Internal | Governance & Oversight, Policies and Codes of Conduct, effecrive crisis management and business; continuity, stakeholder engagmeent and effective communication
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability

## SLC Strategic Risk Register
Strategic Risk Register |  |  |  |  | Dated reviewed by Risk Management Group | [7 empty] | 2026-01-22
[5 empty] | Dated reviewed by SLT | [7 empty] | 2026-01-22
[5 empty] | Next date of review | [7 empty] | 2026-04-30
No. | Date Raised | Link to Quality Indicators / Strategic Aim | Description | Impact Rating (1-5) | Probability Rating (1-5) | Risk Score | Previous submission risk score | Movement since last submission | Adds the score of all open risks | Counts the number of open risks | Adds the score of all being mitigated risks | Counts the number of being mitigated risks | Implications | Mitigation Action | Post-mitigation impact (1-5) DO NOT EDIT | Post-mitigation probability (1-5) | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Progress To Green: Key Actions | Comments | Risk Owner | Risk Oversight | Risk Category | Risk Appetite | AI Risk Assessment
Information
8 | 2021-04-26 | 2.1, 2.5, 2.6, 3.5, 3.6 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 3 | 2 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Impacts on the college's ability to provide a service to its users as well as potential financial and performance impacts. | Shared sector approach in place through HEFESTIS and advanced intelligence. Robust and regular testing of IT systems. Business continuity plans in place for IT and MIS areas. Annual certification with Cyber Essentials Plus. Incident response training. Cyber essentials and cyber controls continue to be monitored, a review on the policies and procedures needs to take place to maintain current levels of confidence. The score can be lower at this review due to the actions being closed down from the audit. Impact remains high, however the probability of the risk can be lowered. | 3 | 1 | 3 | 3 | 0 | Moved to green a low impact as the audit recommendations and completion of regular security reviews continue. No further actions required. | To maintain this risk at green, completion of the audit recommendation for incident response for SLT and continual training of staff will need to be maintained. November 2025 Incident response training for the SLT was undertaken on 19th November. Improvements to the connections of the information systems have also improved following the implementation of the new unit-e system and the API for in-house built systems. We are in the pilot for the cyber observatory with scottish government. January 2026 Improvements to the cyber security platform continue and the board will have sight of the next cyber bi-annual report in May which should also show key progress. As this is a green item already, the mitigations are still in place and the score can stay the same. We also complete a incident response training with the SLT in November to further strengthen the mitigations and establish the responsiblities that the team has with cyber security. | Head of Digital | VP - Finance, Resources & Sustainability | Information | Cautious | Risk: AI is being used to cleverly attack systems and users with more targeted attacks on systems. However, is also being used to identify these types of attack before they happen. By default the attackers are always in front of the defender in cyber security however, the AI learning the patterns means the gap is now much closer. Should the Score Change: Not at this stage but should form part of the monitoring within our cyber framework. We've not seen enough AI-led attacks in the sector and world to believe this is going to be an increase in risk probablity
Finance
1 | 2021-04-26 | 3.1, 3.5, 3.6 | That the College cannot maintain financial stability | 5 | 4 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | That the College would not be able to meet its financial obligations and /or that investment in student activity could not be maintained to an appropriate level. | Awaiting indicative funding for the next academic year in March 2026. Indications are 2% increase, but will not know for sure until SFC update the sector. Value for Money Group focus on staffing efficiencies and more robust Curriculum Planning model. "Flat cash" settlements for 2024/25 and 2025/26 copnfirmed by SFC. Board approved a deficit budget for 2025/26. Management working towards balanced budget. Financial Modelling being undertaken, review of curriculum and ensuring areas that meet demand are promoted. Full cost targets increased. | 5 | 4 | 20 | 20 | 0 | November 2025 The recruitment of the Head of Business Innovation is still ongoing. The team are still active, but until this role is filled, there will be a limit on the progress that can be made. January 2026 Head of BI is still pending. The college are also awaiting the Indicative Funding from the SFC (expected March). The recent Government Budget release has given some optimism to the Sector, but we are not in a position to predict the funding split as yet. | July 2025 The Jun25 FFR return, forecasting the next three years financial position, shows a challenging time for the college, and the sector as a whole. The college are aware of what needs to be done to ensure we are sustainable, but it will take a huge effort to get there. The risk score therefore reflects this. January 2026 The college will soon welcome the Internal Auditors onsite in February to begin work on the Finance Sustainability audit. Updates will be given in the next quarter. | Head of Finance | VP - Finance, Resources & Sustainability | Financial | Cautious | Risk: AI can be used to upskill staff and students, which then may result on the college business model having to change. Should the Score Change: Not at this point.
2 | 2021-04-26 | 3.1, 3.2 3.5, 3.6 | That there is a failure of financial controls | 5 | 3 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | Insufficient or incorrect information available to senior management and the Board of Management; potential for fraud. | Finance Dept team enhanced with permanent appointment of Management and Financial Accountants. Additional support re Procurement from APUC. Extensive work has been undertaken in conjunction with Governance Professional to update policies and procedures. Review of timetable of activities of the Audit and Risk Committee and Finance and Risk Committee now drawn up. Additional work has been undertaken by internal audit service on policies and procedures. Internal and external audit continues to offer significant value in assessing the effectiveness of our overall control environment. Similarly,quarterly reporting to the Board allows areas of concern to be reviewed and monitored. Enhanced payroll controls as a result of iTrent as the lead payroll system. | 5 | 3 | 15 | 10 | 5 | November 2025 The 2025/26 schedule of Internal Audits will be finalised soon, and as per each year there will be focus on Financial Controls. Additionally, the Executive team are working on a Finance Improvement Plan to help speed up the mitigations of controls. January 2026 There is work nearing completion on the 'Finance Plan 2026' which will look to plot all key finance related processes, and deadlines, and will assign ownership and delivery dates for the calender year ahead. This will be reviewed on an ongoing basis, to ensure the college continually meets the expectation of strong financial control. | November 2025 No updates to the risk score this quarter. With the implementation of the Finance Improvement plan, there will be additional resource to allow Finance to focus more on the Finance Controls. Scoring in future quarters should reflect this. January 2026 Finance has started the new calendar year with full staff resource. The department have successfully recruited a Financial Accountant who will focus on improving the financial controls. Payroll continues to evolve, with close links to Finance to improve the output from monthly payroll reporting. | Head of Finance Head of People Services | VP - Finance, Resources & Sustainability | Financial | Cautious | Risk: AI can be a useful tool in highlighting control areas to be focused on, and may also help with the controls themselves. Finance management will need to be vigilent on any outputs, to ensure accuracy, and assurance that the controls are indeed fit for purpose. Should the Score Change: No. The use of AI in this space hasn't begun yet.
3 | 2021-04-26 | 1.6, 2.2, 2.4 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 5 | 3 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | Clawback of SFC activity funding and shortfall in income. Failing to meet credit targets on a consistent basis may affect annual activity allocation. Failure to maintain ESF records to substantiate our claim is likely to affect income. | Student activity is monitored on a fortnightly basis by senior management via the SLT meetings, with reports being made available to faculty and admissions staff; Additional enhanced reporting in use through Power BI to monitor real time information. Credit activity is monitored closely and plans are put in place to meet the gap, such as the preparation of study courses and additional courses following student intakes. | 5 | 2 | 10 | 10 | 0 | July 2025 The college has exceeded the credit target for 24/25. November 2025 Not all curirculum areas recruited to target in August. This is being addressed with an increase in courses due to start in January 2026. | November 2025 The number of CITB classes was lower than expected. This is being addresed with the recruitment of additional National Progression awards. Recruitment is being actively monitored by the CLT. January 2026 At the point of review January recruitment appears to be robust, on-target to achieve full class groups where anticipated. Should this not maximise the credit target, additional recruitment will take place in February and March 2026. January recruitment is currently underway and looking positive. | Head of Curriculum Head of Digital | VP for Student Experience and Innovation | Financial | Cautious | Risk: AI tools require clean, connected data. Fragmented systems may prevent accurate tracking of delivery metrics. If AI is used to automate reporting or decision-making without proper oversight, errors may go unnoticed. Should the Score Change: Keep under review
5 | 2021-04-26 | 2.1, 2.2, 2.6, 3.5 | That there are insufficient funds for capital project and maintenance requirements | 4 | 4 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | The College estate is of an age that requires constant monitoring and an appropriate level of funding to address major issues (e.g. building envelope, heating and cooling, lifts, security equipment, etc). Atrium Passenger lifts are in urgent need of replacement. | CAPEX spend is being reviewed quarterly and priority works being carried out to support curriculum delivery and growth. | 4 | 3 | 12 | 12 | 0 | November 2025 Planning is taking place to carry out replacement of 2 lifts and request for emergency funding being made. This work is expected to be carried out next year. January 2026 CAPEX will be monitored more closely in the year year ahead with the need to invest in large scale projects, such as the lift and in Digital. The college will react to the pending projects in view, once indicative funding is announced by the SFC that will advise on the funding available to the college. Colleges Scotland indicated that there will be an additional £8mm available to Scottish colleges from the recent budget release. | November 2025 Structural Report on lifts completed. Applcation for funding being made by the Principal. A successful application will result in CAPEX funds being available for other projects, to be agreed by SLT. If unsuccessful, CAPEX spend in the year will be greatly impacted, so a total review for the year ahead will be needed. January 2026 After our application for emergency funding was declined, discussions will be ongoing as to how we shape the CAPEX landscape for the year ahead, with the evolving prioirty of projects. Details will continue to flow to SLT regularly. | Head of Finance Head of Facilities | VP - Finance, Resources & Sustainability | Financial | Cautious | Risk: The use of AI to assist in the CAPEX planning phase could be beneficial to generate conversation within the CAPEX group. Discussions and decisions should still be controlled by the human element. Should the Score Change: Not at this point.
Governance
13 | 2021-04-26 | 3.1, 3.2, 3.4, 3.5, 3.6 | That there is a failure of Corporate Governance arrangements | 4 | 3 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | That the College would fail in its duties as a public body and charity to adhere to statutory expectations. Risk to business delivery; risk to reputation; risk to strong governance ensuing impact on operational delivery. | Training and induction for new Board members takes place as needed for new members with support from the College Development Network. Board Development Day undertaken in November 2025. External Effectiveness Review has taken place and shows strong governance. OFAM meetings held on a quarterly basis also demonstrate robust goverance. | 3 | 2 | 6 | 6 | 0 | November 2025 Interview process for new dynamic board members to ensure full complement of members. Induction process is robust. Board members work closely with management team to provide support and advice. Principal and Governance professional are members of the Good Governance Steering Group. Continue the Governance Rolling Review. | It has been recognised by the Scottish Government and the SFC that the delay in announcing Regional Chairs' appointments following dissolution was not the fault of the college. | Governance & Compliance Professional | Principal | Governance | Minimal | Risk: Poor AI oversight or biased algorithms could undermine transparency and accountability, creating governance gaps. Should the Score Change: Not in this quarter.
Health and Safety
6 | 2021-04-26 | 1.1, 1.2, 1.3, 1.4, 2.1, 3.1, 3.3 | That there is a failure to meet statutory and legislative health and safety | 5 | 3 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | Impacts on safety of all employees and students leading to serious injury or death. Unable to protect our most vulnerable students. | Health and Safety Committee meet regularly to monitor health and safety arrangements and any issues are raised. Staff induction in place on H&S; Facilities Teams and H&S Advisor ensure all risk assessments are updated annually; Regular reporting on Health and Safety to HR Committee as part of their remit requirements; Full review of Health and Safety Policy and Procedures being undertaken; Lead Safeguarding Officers in place and appropriate training in place.; Safeguarding group meets regularly. Robust HMI Safeguarding report received; Refresher training and reissue of safeguarding cards; Expanded the network of safeguarding officers; Health and Safety audit completed, with no major recommendations; Appointment of 2 permanent health and safety staff members. Health and Safety Audit completed satisfactorily. Health and Safety Policy approved by the Board of Management. Health and Safety Policy launched and names of those who have read it recorded. Progress made against internal audit plan and Health and Safety Committee meets regularly to keep on top of action and key issues. Policy and procedures updated. H&S Policy reviewed and updated. Continued quarterly H&S committee meetings planned including representation of cross college departments for 2023/24 Reliance upon others within the college, including the Head of Facilities (Previously responsible for H&S) and the previous H&S advisor, now Sustainability Advisor. Generally all items are covered and assistance is also available from others within the college. | 5 | 3 | 15 | 10 | 5 | Annually & Ongoing Continue to review and update H&S Policies as required. | November 2025 New H&S Advisor appointed and working within the People Services team. People Service Advisors provide first point of contact for H&S matters, adding scalability and enhanced engagement across the business. College-wide health surveillance risk assessment being conducted before working with Occupational Health on the implementation of the identified risks. Implementation of enhanced Site Walks, inclusive of health & safety. Student Association now part of the H&S Committee and student H&S data also considered in reporting. Head of Facilities providing Technical support on a ongoing basis. January 2026 H&S advisor has relocated to a new role in the college. The current H&S vacancy should be considered a priority. | Head of People Services Head of Facilities | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | Risk: AI may be used from a reporting a template producing perspective. However, this will be reviewed from a human perspective before progressing, checking against standards such as the HSE. Should the Score Change: No.
Legal/Compliance
4 | 2021-04-26 | 2.1, 2.5, 3.4, 3.6 | That there is a breach of legislation and associated regulations in relation to HR, Quality, Finance and GDPR | 2 | 3 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Breach or leak of sensitive data impacting on college reputation. | Data Protection Officer in place to advice on general Data Protection Regulation; Staff mandatory training and policies in place and actively marketed to heighten awareness; Compliance/audit checks in place; GDPR policies currently being updated as part of College-wide policy refresh exercise; Training planned for all staff on legislative and regulatory issues, including conflict of interest, bribery and corruption and security of assets. A suite of new polices have been developed and/or updated; Multi factor authentication in train; Cyber security Essentials status obtained; Training completed on conflict of interest etc as above and data protection and GDPR. Cybersecurity audit completed satisfactorily. College is now undertaking penetration testing; All staff conference in Novust; all staff completed mandatory training on GDPR; Data Protection portal is now live. New retention policy has been agreed and published. Cyber Essentials plus was successfully completed. GDPR TES develop training issued to all staff, ICO framework and ROPA for each department. Work has begun on ROPA's (records of processing) and the ICO accountability framework has been completed giving SLC a confidence of data protection controls. Cyber security frameworks and changes continue to be reviewed and we are confident in the controls that are in place from the NCSC 10 things | 2 | 2 | 4 | 4 | 0 | July 2025 All data protection tasks have been transferred from MIS to Governance. An important task (Records of processing activities - ROPA) is part complete, about 60-65%. Governance will aim to tackle the remaining departments asap. ETA for completion of this is Dec 2025. November 2025 HR, Quality and Finance regulations will now be monitored within this risk, specifically around Data Protection. Governance will work with each area to monitor the outcomes from all relevant audits in these areas. | Data protection team have worked through a number of ROPA with each area and are currently pulling together Info Asset Register. November 2025 Other areas of compliance are to add to the comments and tasks of this risk, will raise with the group. This includes financial, quality and People Services compliance requirements. The current implications is a breach of data only, that needs expanded and the risk assessed based on any new implications. All Heads of Department are to continually provide technical support to ensure no breaches are made. All legislative updates should be reported to the VP - Finance, Resources & Sustainability. January 2026 Work ongoing within the college to ensure the legislations relating to each area are imbedded through all policies. Project being led by governance professional, but all heads of department accountable for their areas. | Head of Digital Head of Finance Head of People Services Head of Facilities Head of Quality | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | Risk: It is key that AI is treated like any other software and is assessed by the IT department before usage. We already use a software register and can complete data protection impact asessments (DPIA's) to determine if the data being stored is safe. In some cases, the firewall has been blocking any unknown or potentially risky AI software and there is already a culture within the staff to "ask IT" before proceeding if there are AI tools that could be used. Should the Score Change: AI could improve the compliance checks as we start to use it more within our day-to-day. We should monitor this closely due to the uncertainty of the software that is emerging e.g. some software that is used to track usage or use our data for "teaching" the AI. This should be more cautious and mitigations may need to be put in place.
11 | 2022-02-04 | 2.1, 2.3, 2.5, 2.7, 3.1, 3.2, 3.4, 3.6 / Aim 1 | That there is a failure to safeguard the health and wellbeing of staff and students. | 3 | 3 | 9 | 9 | 0 |  |  |  |  | Impacts on the health and wellbeing of staff and students. This could result in high absence, disengagement and higher withdrawal rates for students. Risk of serious harm to the individual if the appropriate safeguarding action is not taken. This would significantly impact the student and staff experience leading to potential risk of legal action, complaints and having a negative impact on the college reputation. | Student Welfare - Duty of Care Audit - Graded Good. Going to ARC/LTSE Committee Aug 2025. Ongoing effective development of safeguarding and health and wellbeing support for staff and students. Safeguarding / GBV Prevention / Corporate Parenting / Carers Support policies and procedures in place. Specialised staff in Student Services and HR responding to concerns or issues. Criminal Convictions and PVG is undertaken as part of the employee recruitment process. Safeguarding, Prevent and Corporate Parenting training is mandatory as part of the staff induction process. Safeguarding including Prevent, Corporate Parenting, Mental Health & Wellbeing information and videos part of the Learner Induction process. College Safeguarding Group is a cross-college group which has both student and staff membership - this group meets quarterly. GBV Prevention Strategy and Action Place / Corporate Parenting Plan in place which is monitored by the Safeguarding Group. Other mitigations include:- •Student Support email address. Same day response, including responses to financial and emotional crisis support. •Guidance and support staff available on campus for in person support on same day appointment basis. •Staff are trained in Mental Health First Aid and ASIST •Dissemination and attendance of external safeguarding training opportunities, such as those provided by CDN, •Counselling Service for staff and students. •Weekly Yoga and Mindfulness classes for staff and students •Same day response provided via dedicated student support email, including responses to financial and emotional crisis support. •Guidance and support / line management staff available on campus for in person support on same day appointment basis. •Annual safeguarding, health and wellbeing calendar of events •Peer support groups for staff and students. | 3 | 1 | 3 | 3 | 0 | November 2025 The College is engaging with the cross-college Health & Safety group for the implementation of Martyn's law. The College is revising it's Disciplinary Policy and Procedure, in line with the national Policy and Model Procedure - discussions are ongoing with locally recognised trade unions. The introduction of enhanced Site Walks will include a review of safeguarding measures and collateral across the entire College. The Safeguarding Policy and Procedures is revewed on an annual basis. This is approved by the Board with the last approval taking place August 2025. | January 2026 Very positive Student Association audit report received with a Grading of Good being given alongisde a number of key strengths identified. Work undertaken on the Emily Charter, again with positive results. The College has successfully retained the GBV Charter for Colleges and Universities following the Annual Review process. Emily Test GBV Risk Assessment training being delivered to the College's Safeguarding Network in February 2026. | Head of Student Services Head of People Services | VP for Student Experience and Innovation | Legal/Compliance | Cautious | Risk: Deploying AI tools without clear communication or opt-in policies may cause alarm or violate standards. Potentially not leveraging AI for positive wellbeing tools (e.g., mental health chatbots, workload balancing, wellbeing dashboards) could present a risk in the future. Should the Score Change: Keep under review
15 | 2023-10-26 | 2.6, 2.7, 3.1, 3.2, 3.4, 3.5, 3.6 | That the College is not on track to meet the Scottish Government net zero sustainability priorities. | 3 | 3 | 9 | 9 | 0 | 0 | 0 | 0 | 0 |  | College has drafted a new Climate Change Emergency Action Plan, based on the Further and Higher Education road map, which will go to the Finance and Resources Committee on 15 November 2024. College works very closely with the Energy Skills Partnership to deliver on national skills agendas. College submits the Public Body Climate Change annually. Carbon emissions are monitored weekly. The Climate Change Action Team (CCAT) monitors and promote climate change actions throughout the College. | 3 | 2 | 6 | 6 | 0 | LED lighting replacement programme. The replacement of 1900 lights to LED fittings. Additional Solar Panels fitted. The PV system comprise of 300 panels to give an additional output of 150kW. Scottish Green Public Sector Estate Decarbonisation Scheme. The College has engaged with Mott MacDonald regarding pre capital works to investigate the Central Government Energy Efficiency Capital Grant Fund 2023/2024 to support the College journey to NET Zero. January 2026 Government has cut funding from £800mm to £400mm, as advised by Colleges Scotland. The college is delveloping a partnership with Climate Action Strathaven. | Note the College was not built with net zero in mind so the College is working on finding solutions through the funding being offered by the Scottish Government to support with a fabric first approach. August 2025 Ongoing Net Zero initiatives are being progress by the CCAT and Facilities in alignment with the Scottish Government's target. The Public Body Climate Change Duties Report (PPCCDR) will be submitted by November 2025 using the existing template pending release of the revised version. January 2026 New Sustainability Advisor has been appointed and has met with the Sustainability Leads to assist in driving the college to meet carbon targets. | Head of Facilities Head of Curriculum | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | Risk: AI can assist in meeting sustainability priorities by optimising energy usage, predicting carbon outputs, and supporting data-driven decisions for emissions reduction. However, failure to adopt AI for efficiency improvements could slow progress toward net zero targets, increasing compliance risk. Should the Score Change: Not at this point.
Operations
9 | 2021-04-26 | 1.1, 1.2, 1.3, 1.4, 1.5, 1.6, 1.7, 2.3 | That there is a failure to achieve high standards of learning, teaching and assessment. | 4 | 3 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | Impacts on the student experience, the college's reputation and Education Scotland risk ratings. Impacts on student recruitment leading to financial risk. | First self-evaluation cycles completed and progress reviews have taken place. Ongoing engagement and campus visits from HMI. Audit cycle in train. Robust learner voice processes which are acted on promptly. Evaluation process updated and self evaluation progress occuring. HMIE Education Scotland visit took place in March 2023 which resulted in no main points for action. Self Evaluation written. Care Review and HMIE Inspectorate visits assessed learning environment to be appropriate. | 4 | 1 | 4 | 4 | 0 | Mitigating actions in place. External assessors being used to assess Construction MAs, now part of the Quality Audit process to provide assurance that work is of a high standard and does not impact on direct claims status. Education Scotland annual engagement visit report received which did not contain any main points of action. Current challenges with missing outcomes due to ASOS, as yet there is not a national approach to ASOS, and there has been no communication from the Scottish Funding Council. The impact of this may mean that results nationally will not be available in March 2024. Care was the subject of a national thematic review in early 2024 by Education Scotland. | August 2025 Positive outcomes from EV activities and identification of good practice across the curriculum reduce the risk of non-compliance and support continuous quality improvement. | Head of Curriculum | VP for Student Experience and Innovation | Operations | Open | Risk: Not leveraging AI-powered adaptive learning platforms. Use of AI in grading or assessment without proper calibration or oversight. Failure to use AI analytics to monitor teaching effectiveness, learner engagement, or curriculum alignment. AI tools may not be accessible to all learners due to device, connectivity, or support gaps. Using AI tools without embedding them in sound teaching practice. Should the Score Change: Keep under review
12 | 2021-04-26 | 1.1, 1.2, 1.3, 1.4, 1.5, 1.6, 1.7, 2.5, 2.6, 2.7, 3.1, 3.3 | That the College cannot provide a robust learner experience supporting them onto their positive destinations. | 4 | 2 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | Relates to application and recruitment experience, students not receiving the appropriate or accurate information or the necessary access to support such as financial or health and wellbeing. Recruitment impacted by outdated systems impacting the experience. Also any delays to bursaries, additional IT equipment and discretionary support may impact. | Applications are monitored by the Student Services Team, review of application and enrolment system in train. Financial and emotional support offered by the Team. Team undertake regular training to provide the best possible service and to keep up to date with changes. Power BI now being used for curriculum planning and to ensure a more efficient application process. Other mitigations include •Same day response provided via dedicated student support email, including responses to financial and emotional crisis support. •Guidance and support staff available on campus for in person support on same day appointment basis. •Ongoing review of new Admissions electronic system to ensure smooth transition from application to enrolment. Additional work to be undertaken in this area via regular working group meetings. •Staff attendance at new Mental Health First Aid training, as provided by SLC. •Dissemination and attendance of external training opportunities, such as those provided by CDN, etc. •Review potential increase in counselling and guidance/support provision to ensure reduction in waiting times for emotional support. •Bursary software under review with developers. •Support being provided to SA including additional recruitment of new VP. •Provision of long term laptop loans via Library service to facilitate engagement in class and coursework. Reinforced links between the student association, class reps and quality team so directly links back to the learner More opportunities for students to undertake study skills in this academic year and it has now been introduced into twilight sessions. The vast majority of applications and students are progressed on a timely basis, however, further actions are being taken to ensure consistency across the college. Updated Student Association Student Mental Health Agreement (SMHA) produced. | 4 | 1 | 4 | 4 | 0 | Mitigating actions in place or in development. 2025-2026 CDN Agreement agreed with SLT. Additional support being provided to SA via the Quality and Learning & Teaching Innovation Unit. Laptop bank pilot scheduled for mid-year 2025-2026. Power BI dashboards nearing completion and roll-out for use in curriculum planning. | November 2025 Curriculum planning meetings have taken place across all curriculum areas supported by stakeholder engagement, industry patterns, and future skills requirements. Programmes are designed to delivery opportunities for skills development using innovative approaches to learning and teaching that prepare students for progression pathways. January 2026 Preliminary Student Association audit has taken place, with positive results. Work undertaken on the Emily Charter, again with positive results. The College’s Data and Report Plan includes requests for tracked College Leaver Destinations in all 4 key modes of delivery, and a dashboard publicising/capturing the most recent SFC verified data. The Principalship and QLTI are exploring the viability of reinstating Student Question Time prior to Spring Break. | Head of Quality and Learning and Teaching Innovation | VP for Student Experience and Innovation | Operations | Open | Risk: Failure to adopt AI tools (e.g., adaptive learning platforms, intelligent tutoring systems) could widen the gap between learner needs and institutional support. Delegating too much to AI (e.g., chatbots for student support or automated career guidance) without human backup could lead to poor learner experiences. If AI is used for admissions, grading, or learner analytics, biased algorithms could disadvantage certain student groups. Should the Score Change: No, but keep under review.
People
10 | 2021-04-26 | 2.1, 2.3, 2.6, 3.1, 3.3, 3.4 | That there is a failure to provide an engaging and effective employee journey. | 4 | 4 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | Impact on the employee experience and could result in high turnover, high absence rates, disengagement, poor employee relations and industrial relations matters, poor performance of employees and subsequently a poor experience for students and negative impact on college reputation. | Accreditations achieved to date include: Disability Confident Employer and Leaders in Diversity. The re-accreditations of Investors in People and We Invest in Wellbeing are currently being progressed; Ongoing review of the employee journey, process optimisation and automation. Consideration for a new HR System; Refreshed policies and procedures include: Attendance Management and Support Procedure; Disciplinary Procedure; Grievance Procedure and the Public Interest Disclosure Policy and Procedure. Employee Journey being mapped out and associated procedures being drafted, with a view of lean process management and consideration of both automation and employee experience. People Managers being trained on disciplinary, grievance and investigations by ACAS. Review of payroll and pensions process. The College now has We Invest in Well Being Platinum. New integrated HR & Payroll system on track to be implemented in 2023. Pension reporting streamlined. More resilence in HR team with regards to learning how to do payroll. Wider HR team now trained to administer payroll. | 4 | 2 | 8 | 8 | 0 | July 2025 The college has gone through the VS process, with HR working hard to close out the final questions around this. With the new academic year upon the college there is a focus on the upcoming Staff Conference and Employee Development day. There will be further enhancement in this area when iTrent releases more functions for all staff. The creation of the People Services team (bringing together HR, Equality & Health & Safety) has given the opportunity to enhance business partnering across the business for all HR, Equality and Health & Safety matters. November 2025 New People Service Advisor role being implemented, each with specific departments to focus on, to help enhance the employee journey through advice, solutions and support for management and employees. Internal training and coaching will develop the incumbents to be able to represent all of People Services with their stakeholder groups. Modules on iTrent continue to be implemented, enhancing the transparency and access to data for managers and employees. | January 2026 The college continues to review staff polices and procedures in line with priorities agreed with PAC, employment law changes and NJNC agreements. New policies currently under review by PAC include Employee Learning and Development ; Staff Recruitment and Employee Transition and Departure. These are new policies for the college and once implemented will provide clear frameworks to managers and employees to support consistent approaches to an effective employee journey. The team is participating in internal itrent training for new itrent modules to be rolled out including career reviews and recruitment. Guides will be available to all staff regarding itrent and the PS team is developing a skills base to be able to respond to employee queries on the new system. | Head of People Services | Principal | People | Eager | Risk: AI may be used from a reporting a template producing perspective. However, this will be reviewed from a human perspective before progressing, checking against standards such as the CIPD and legislation. Should the Score Change: No
Property
7 | 2021-04-26 | 2.1, 2.5, 2.6, 3.5, 3.6 | That there is business interruption due to major disaster, IT failure etc | 3 | 5 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | Impacts on the college's ability to provide a service to its users as well as potential financial and performance impacts. | Business Continuity Plan for College in place. Business interruption insurance in place. Member of HEFESTIS and benefit from shared intelligence. Cyber Security information will be placed into the next risk about theft of major systems. Business continuity updates in progress. Cyber security controls continue to be improved following the cyber risk framework. Work started on the BCP and incident response documentation as it needs revisited since it was published. | 3 | 4 | 12 | 12 | 0 | November 2025 Work continues on the above documentation from August 25 and BIA's, please see comments for future developments. SLT had an internal Business Interuption training session in November to bring BCP and the risk of Interuption to the forefront of SLT's thinking. This will be an annual session. January 2026 There are a number of action to progress this to a green score, however not at this review. Please see the notes for progress that has already been made. | The College had a developed Business Continuity Plan embedded prior to the COVID pandemic and has built on that via infrastructure improvements and additions utilising additional SFC ring-fenced funding. November 2025 Work has begun on the SLC BCP documentation, beginning with a refresh of the document initially with further work between now and March when we will be audit by HL. We will also be conducting BCP testing and areas of training throughout the year, more details in the coming months. The score won't move until this work is completed and SLT and the board are assured of the work satisfies the college can maintain operations when there is an incident January 2026 Incident repsonse training took place for the SLT in November and then was actually tested with an incident with the lift very shortly after that. The incident training expose some actions that needed to be addressed which are in progress. The Business Continuity documentation had been updated however, the audit for this to take place in March. | Head of Digital | VP - Finance, Resources & Sustainability | Property | Minimal | Risk: We are already heavily reliant on software to run the college, the risk of using an AI model/software could increase the reliance and it is important to not loose sight of the business operation. That said, the use of AI for understanding gaps in our BCP planning and alerting SLT and managers to potential incoming failures is something we should explore, finance permitting. Should the Score Change: There is already a lot of work to do on the BCP documentation which AI can play a part in. For it to effect the score solely on the good and bad things AI brings to this risk is not necessary at this stage. The risk of software reliance already exists within the college, adding the AI tools behind that means the risk is still the same.
Strategy
14 | 2023-01-24 | 2.3, 3.2, 3.3 | That there is a reputational risk to the College. | 4 | 3 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | •That potential students, staff or Board members are deterred from enrolling / joining the College. •That the College suffers financial loss from a decrease in activity or loss of access to potential income streams. | • Staff development sessions on, for example, inclusiveness and diversity being part of mandatory training for staff; • Regular staff meetings including annual all-staff conference; • College has complaints procedure, clearly highlighted on website; • Extensive governance training for senior staff and Board members being delivered as part of a rolling programme of development. -Updated social media policy -"Good news" stories shared and positive messaging. -Good liaison with external stakeholders -Comms plan developed to support with any negative press -Quality Assurance policies and procedures in place to support compliance, maintain the SQA Devolved Authority Status, and the approval to deliver a range of Awarding Body provision and qualifications. -Robust self-evaluation and Action Planning OFAM meetings on a quarterly basis, demonstrate robust goverance. | 3 | 3 | 9 | 9 | 0 | Effective Comms plan in place Positive Engagement with Trade Unions to support employee relations Employee engagement framework Social Media Guidelines now in place Annual Awarding Body Internal Systems Verification activity. Positive External Effectiveness Review completed OFAM meetings on a quarterly basis, demonstrate robust goverance. | November 2025 Board induction for new members. Board development day in Nov 2025 Principal and Gov Professional on Good Governance Steering Group. January 2026 SLT are currently developing the management training program with CDN. There is an ongoing focus on progressing the positive view of the college throughout the campus, and the local community. Stakeholder engagement approach also in train. | All Heads of Department | Principal | Strategy | Open | Risk: Misuse of AI (e.g., biased decisions or privacy breaches) could trigger negative publicity, amplifying reputational damage. Should the Score Change: Not as a result of AI assessment.
|  |  |  | Risk Key | Low | 1-3 | [8 empty] | Risk Key | Low | 1-3
[5 empty] | Medium | 4-9 | [9 empty] | Medium | 4-9
[5 empty] | High | 10-19 | [9 empty] | High | 10-19
[5 empty] | Very High | 20-25 | [9 empty] | Very High | 20-25

## SLC Board Risk Appetite
SLC Board Risk Appetite | Dated reviewed by RMG | 2026-01-22 |  |  | Risk Appetite Rating | Count
Summary | Dated reviewed by SLT | 2026-01-22 |  |  | Averse | 0
| Next date of review (Exp. not actual) | 2026-04-30 |  |  | Minimal | 2
[5 empty] | Cautious | 5
Risk Category | Current Rating | Comments | Average Risk Score from RR | Risk Numbers | Balanced | 0
Strategy | Open | Guiding principles or rules in place that are receptive to considered risk taking in organisational actions and the pursuit of priorities. Organisational strategy is refreshed at 2-3 year intervals | 9 | 14 | Open | 5
Operations | Open | Innovation supported, with clear demonstration of benefit / improvement in management control. Responsibility for noncritical decisions may be devolved. | 4 | 9, 12 | Eager | 1
Legal/Compliance | Cautious | Want to be reasonably sure we would win any challenge. | 7.3333 | 4, 6, 11, 15
Property | Minimal | Recommendation to follow strict policies for purchase, rental, disposal, construction, and refurbishment that ensures producing good value for money. | 12 | 7
Financial | Cautious | Seek safe delivery options with little residual financial loss only if it could yield upside opportunities. | 14.25 | 1, 2, 3, 5
Commercial | Open | Innovation supported, with demonstration of benefit / improvement in service delivery. Responsibility for non-critical decisions may be devolved. | Category not used | n/a
People | Eager | Innovation supported, with demonstration of benefit / improvement in service delivery. Responsibility for non-critical decisions may be devolved. | 8 | 10
Technology | Open | Systems / technology developments considered to enable improved delivery. Agile principles may be followed. | Category not used | n/a
Information | Cautious | Accept need for operational effectiveness with risk mitigated through careful management limiting distribution | 3 | 8
Security | Cautious | Limited security risks accepted to support business need, with appropriate checks and balances in place: • Adherence to FCDO travel restrictions • Vetting levels may flex within teams, as required • Controls managing staff and limiting visitor access to information, assets and estate. • Staff personal devices may be used for limited official tasks with appropriate permissions. | Category not used | n/a
Project/Programme | Open | Innovation supported, with demonstration of commensurate improvements in management control. Responsibility for noncritical decisions may be devolved. Plans aligned with functional standards and organisational governance | Category not used | n/a
Reputational | Cautious | Appetite for risk taking limited to those events where there is little chance of any significant repercussion for the organisation. | Category not used | n/a
Governance | Minimal | Willing to consider low risk actions which support delivery of priorities and objectives. Processes, and oversight / monitoring arrangements enable limited risk taking. Organisational controls maximise fraud prevention, detection and deterrence through robust controls and sanctions. | 6 | 13
Risk Appetite Rating | Explanation
Averse | The organization avoids risk and uncertainty.
Minimal | The organization prefers low-risk options that may only offer limited rewards.
Cautious | The organization prefers safe options that may only offer limited rewards.
Balanced | The organization accepts that some risk is involved in activities, but is prepared to monitor and mitigate it.
Open | The organization is willing to consider all options and choose the one that will deliver success while providing an acceptable level of reward.
Eager | The organization is eager to be innovative and choose options that may offer higher rewards, even if they have greater risk.
Risk Key
Low | 1-3
Medium | 4-9
High | 10-19
Very High | 20-25

## SLC Risk Profile & Scorin
SLC STRATEGIC RISK PROFILE & SCORING
Likelihood |  | Risk Profile |  |  |  |  | Assessing Overall Risk And Risk Threshold
Very high (76% or more chance of occurring within the next 12 months) | 5 | 5 | 10 | 15 | 20 | 25 | Risk Level | Score | Risk Level Description
High (51-75% chance of occurring within the next 12 months) | 4 | 4 | 8 | 12 | 16 | 20 | Very High | 20-25 | Rating: Unacceptable level of risk exposure defined as an extreme impact risk that requires immediate Additional Mitigation to include a Control Action Plan as well as Risk Control Measures to be applied. Reporting: To Principals and RSB.
Likely (26-50% chance of this occurring within the next 12 months or is likely to occur at least once every 1 to 3 years) | 3 | 3 | 6 | 9 | 12 | 15 | High | 10-19 | Rating: Manageable level of risk which requires Risk Control Measures to be put in place to reduce exposure. Reporting: Chair of the Regional Strategic Risk Management Group and Audit Committee.
Possible (6-25% chance of this occurring within the next 12 months or is likely to occur at least once within the next 3 to 10 years) | 2 | 2 | 4 | 6 | 8 | 10 | Medium | 4-9 | Rating: Acceptable level of risk exposure subject to regular Targeted Monitoring. Risk Control Measures may be required in support of active monitoring Reporting: Regional Strategic Risk Management Group / Senior Management Team.
Remote (1-5% chance f occurring within the next 12 months or may occur in at least 10 years time | 1 | 1 | 2 | 3 | 4 | 5 | Low | 1-3 | Rating: Acceptable level of risk subject to regular Routine Monitoring. Reporting: Regional Strategy Risk Management Group Risk Management Group / Senior Management Team.
Multiplier |  | 1 | 2 | 3 | 4 | 5
Impact on achieving objectives |  | Negligible Impact | Minor impact | Moderate impact | Major impact | Catastrophic impact.
|  | Negligible Impact | Minor impact | Moderate impact | Major impact | Catastrophic impact.
Finance |  | e.g. Loss of income inc. associated costs of up to £100,000 | e.g. Loss of income inc. associated costs of between £100,000 and £500,000 | e.g. Loss of income inc. associated costs of between £500,000 and £1,000,000 | e.g. Loss of income inc. associated costs of between £1,000,000 and £2,000,000 | e.g. Loss of income inc. associated costs of more than £2,000,000
Staff |  | e.g. limited staff lost, on-going absenteeism | e.g. loss of a number of key staff, health / illness, shrinking skilled labour market | e.g. significant loss of key staff, defection to competitor, strike action, drop in morale due to new delivery issues | e.g. loss of key staff, mass defection to competitor, lengthy strike action, drop in morale due to loss of key staff | e.g. loss of large numbers of key staff due to severe epidemic ; very long strike action
Service |  | e.g. small fall in service levels, some minor quality standards are not met | e.g. moderate fall in service levels, major partner relationships strained | e.g. significant fall in service levels, serious strain on learner relationship | e.g. significant fall in service levels, deterioration in academic standards, learner dissatisfaction | e.g. catastrophic fall in service levels, significant loss of learner nos, failure of academic standards
Stakeholder |  | e.g. Affects only one group of stakeholders with minimum impact on performance | e.g. Affects more than one group of stakeholders but only short-term impact on reputation | e.g. Affects more than one group of stakeholders with widespread medium-term impact on reputation | e.g. Affects a significant number of major stakeholders with long-term impact on impact on reputation | e.g. Affects all major stakeholders with long-term impact on public memory causing damage to reputation
Original Scoring from SLC RR | [6 empty] | Board Appetite Levels
Score |  | Risk Level |  |  |  |  | Risk Category | Rating | Comment
1 |  | Low | Green |  |  |  | Commercial | Open | Entrepreneurial
2 |  | Low | Green |  |  |  | Data / Info Management | Minimal | Cyber security/Data protection
3 |  | Low | Green |  |  |  | Finance | Minimal | Cannot hold reserves
4 |  | Low | Green |  |  |  | Governance | Averse | Compliance is mandatory
5 |  | Medium | Amber |  |  |  | Health and Safety | Open | Entrepreneurial
6 |  | Medium | Amber |  |  |  | Legal/Compliance | Averse | Strict compliance
7 |  | Medium | Amber |  |  |  | Learning Teaching & Student Exp. (Operations) | Open | To meet challenge
8 |  | Medium | Amber |  |  |  | People | Averse | People come first
9 |  | Medium | Amber |  |  |  | Project/Programme | Eager | Diversify
10 |  | Medium | Amber |  |  |  | Property | Open | Entrepreneurial
11 |  | Medium | Amber |  |  |  | Strategy | Open | Consistent with Code
12 |  | High | Red
13 |  | High | Red |  |  |  |  | Risk Appetite | Explanation
14 |  | High | Red |  |  |  |  | Averse | The organization avoids risk and uncertainty.
15 |  | High | Red |  |  |  |  | Minimal | The organization prefers low-risk options that may only offer limited rewards.
16 |  | High | Red |  |  |  |  | Cautious | The organization prefers safe options that may only offer limited rewards.
[8 empty] | Balanced | The organization accepts that some risk is involved in activities, but is prepared to monitor and mitigate it.
[8 empty] | Open | The organization is willing to consider all options and choose the one that will deliver success while providing an acceptable level of reward.
[8 empty] | Eager | The organization is eager to be innovative and choose options that may offer higher rewards, even if they have greater risk.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Jul 25 SLC Summary (hidden)
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2025-07-31 | [5 empty] | RSRMG
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2025-07-31 | [5 empty] | Aug 2025
|  |  | Next date of review (Expected not actual) |  |  |  | 2025-10-30
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Oversight | Risk Appetite Category | Risk Appetite | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check!
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of MIS | VP - Finance, Resources & Sustainability | Information | Cautious | 6 | 3 | 0 | 0
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | Head of Finance | VP - Finance, Resources & Sustainability | Financial | Cautious | 20 | 20 | 0 | 0
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | Head of Finance Head of HR | VP - Finance, Resources & Sustainability | Financial | Cautious | 15 | 10 | 0 | 0
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 1 | 5 | 5 | 0 | Head of Curriculum | VP for Learning & Teaching | Financial | Cautious | 15 | 5 | 0 | 0
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 3 | 12 | 12 | 0 | 4 | 3 | 12 | 12 | 0 | Head of Finance Head of Facilities | VP - Finance, Resources & Sustainability | Financial | Cautious | 12 | 12 | 0 | 0
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 5 | 5 | 25 | 8 | 17 | 4 | 5 | 20 | 4 | 16 | Governance & Compliance Professional | Principal | Governance | Minimal | 25 | 20 | -17 | -16
Health and Safety
6 | That there is a failure to meet statutory and legislative health and safety | 2 | 5 | 3 | 15 | 12 | 3 | 5 | 2 | 10 | 8 | 2 | Head of HR Head of Facilities | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
Legal/Compliance
4 | That there is a breach of legislation and associated regulations (incl. HR, Quality, Finance, GDPR) | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of MIS Head of HR Head of Facilities Quality | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Head of Student Services Head of HR | VP for Learning & Teaching | Legal/Compliance | Cautious | 9 | 3 | 0 | 0
15 | That the College is not on track to meet the Scottish Government net zero sustainability priorities. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | Head of Facilities Head of Curriculum | VP - Finance, Resources & Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
Operations
9 | That there is a failure to achieve high standards of learning, teaching and assessment. | 1,2 | 4 | 3 | 12 | 8 | 4 | 4 | 1 | 4 | 4 | 0 | Head of Curriculum | VP for Learning & Teaching | Operations | Open | #N/A | #N/A | #N/A | #N/A
12 | That the College cannot provide a robust learner experience supporting them onto their positive destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 3 | 12 | 12 | 0 | Quality | VP for Learning & Teaching | Operations | Open | #N/A | #N/A | #N/A | #N/A
People | [19 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 4 | 16 | 4 | 12 | Head of HR | Principal | People | Eager | 8 | 16 | 0 | -12
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 5 | 15 | 6 | 9 | 3 | 4 | 12 | 6 | 6 | Head of MIS | VP - Finance, Resources & Sustainability | Property | Minimal | 15 | 12 | -9 | -6
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 4 | 16 | 16 | 0 | 4 | 3 | 12 | 12 | 0 | All Heads of Department | Principal | Strategy | Open | 16 | 12 | 0 | 0
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability

## Apr 25 SLC Summary (hidden)
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2025-04-24 | [5 empty] | RSRMG
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2025-04-24 | [5 empty] | May 2025
|  |  | Next date of review (Expected not actual) |  |  |  | 2025-07-31
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Appetite Category | Risk Appetite | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check!
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of MIS | Information | Cautious | 6 | 3 | 0 | 0
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | VP for Finance, Estates and Sustainability | Financial | Cautious | 20 | 20 | 0 | 0
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | VP for Finance, Estates and Sustainability | Financial | Cautious | 15 | 10 | 0 | 0
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 1 | 5 | 5 | 0 | VP for Learning & Teaching | Financial | Cautious | 15 | 5 | 0 | 0
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 3 | 12 | 12 | 0 | 4 | 3 | 12 | 8 | 4 | VP for Finance, Estates and Sustainability | Financial | Cautious | 12 | 12 | 0 | -4
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | Governance Professional | Governance | Minimal | 8 | 4 | 0 | 0
Health and Saftey
6 | That there is a failure to meet statutory and legislative health and safety | 2 | 4 | 3 | 12 | 12 | 0 | 4 | 2 | 8 | 8 | 0 | Head of Estates | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
Legal/Compliance
4 | That there is a breach of legislation and associated regulations (incl. HR, Quality, Finance, GDPR) | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of MIS | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Executive Team | Legal/Compliance | Cautious | 9 | 3 | 0 | 0
15 | That the College is not on track to meet the Scottish Government net zero sustainability priorities. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | VP for Finance, Estates and Sustainability | Legal/Compliance | Cautious | #N/A | #N/A | #N/A | #N/A
Operations
9 | That there is a failure to achieve high standards of learning, teaching and assessment. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | VP for Learning & Teaching | Operations | Open | #N/A | #N/A | #N/A | #N/A
12 | That the College cannot provide a robust learner experience supporting them onto their postivie destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 3 | 12 | 8 | 4 | VP for Learning & Teaching | Operations | Open | #N/A | #N/A | #N/A | #N/A
People | [18 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | Head of HR | People | Eager | 8 | 4 | 0 | 0
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 2 | 6 | 6 | 0 | 3 | 2 | 6 | 3 | 3 | Head of MIS | Property | Minimal | 6 | 6 | 0 | -3
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 4 | 16 | 16 | 0 | 4 | 3 | 12 | 12 | 0 | Principal | Strategy | Open | 16 | 12 | 0 | 0
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability

## Feb 25 SLC Summary (hidden)
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2025-01-27 | [5 empty] | 0
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2025-02-04 | [5 empty] | February 2025
|  |  | Next date of review (Expected not actual) |  |  |  | 2025-03-22
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Appetite Category | Risk Appetite | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check!
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of MIS | Information | Cautious | 6 | 3 | 0 | 0
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | VP for Finance, Estates and Sustainability | Financial | Cautious | 20 | 20 | 0 | 0
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 3 | 15 | 10 | 5 | VP for Finance, Estates and Sustainability | Financial | Cautious | 15 | 15 | 0 | -5
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | VP for Learning & Teaching | Financial | Cautious | 15 | 10 | 0 | 0
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 4 | 16 | 16 | 0 | 4 | 3 | 8 | 12 | 0 | VP for Finance, Estates and Sustainability | Financial | Cautious | 16 | 12 | 0 | 0
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 3 | 12 | 12 | 0 | 3 | 2 | 6 | 6 | 0 | Governance Professional | Governance | Minimal | 12 | 6 | 0 | 0
Health and Saftey
6 | That there is a failure to meet statutory and legislative health and safety as well as safeguarding requirements. | 2 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 15 | 10 | 5 | Head of Estates | Legal/Compliance | Cautious | 15 | 15 | 0 | -5
Legal/Compliance
4 | That there is a breach of legislation and associated regulations (incl. GDPR) | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of MIS | Legal/Compliance | Cautious | 6 | 4 | 0 | 0
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Executive Team | Legal/Compliance | Cautious | 9 | 3 | 0 | 0
15 | That the College is not on track to meet the Scottish Government net zero targets. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | VP for Finance, Estates and Sustainability | Legal/Compliance | Cautious | 9 | 6 | 0 | 0
Operations
9 | That there is a failure to achieve high standards of learning and teaching. | 1,2 | 4 | 3 | 12 | 12 | 0 | 4 | 1 | 4 | 4 | 0 | VP for Learning & Teaching | Operations | Open | 12 | 4 | 0 | 0
12 | That the College cannot provide a robust learner experience supporting them onto their final destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | VP for Learning & Teaching | Operations | Open | 8 | 4 | 0 | 0
People | [18 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 4 | 16 | 16 | 0 | 4 | 2 | 8 | 8 | 0 | Head of HR | People | Eager | 16 | 8 | 0 | 0
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 5 | 15 | 15 | 0 | 3 | 4 | 12 | 12 | 0 | Head of MIS | Property | Minimal | 15 | 12 | 0 | 0
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 3 | 12 | 12 | 0 | 3 | 3 | 9 | 9 | 0 | Principal | Strategy | Open | 12 | 9 | 0 | 0
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability

## Nov 24 SLC Summary (hidden)
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 2025-01-22 | [5 empty] | 0
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 2025-01-22 | [5 empty] | February 2025
|  |  | Next date of review (Expected not actual) |  |  |  | 2025-04-22
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner | Risk Category | Nov previous risk score | Nov post-mit score | Edit Check! | Edit Check!
Data / Info Management
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of MIS | Data / Info Management | 6 | 3 | 0 | 0
Finance
1 | That the College cannot maintain financial stability | 3 | 5 | 4 | 20 | 20 | 0 | 5 | 4 | 20 | 20 | 0 | VP for Finance, Estates and Sustainability | Finance | 20 | 20 | 0 | 0
2 | That there is a failure of financial controls | 3 | 5 | 3 | 15 | 15 | 0 | 5 | 3 | 15 | 10 | 5 | VP for Finance, Estates and Sustainability | Finance | 15 | 15 | 0 | -5
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,2,3 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 10 | 10 | 0 | VP for Learning & Teaching | Finance | 15 | 10 | 0 | 0
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 4 | 16 | 16 | 0 | 4 | 3 | 12 | 12 | 0 | VP for Finance, Estates and Sustainability | Finance | 16 | 12 | 0 | 0
Governance
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 3 | 12 | 12 | 0 | 3 | 2 | 6 | 6 | 0 | Governance Professional | Governance | 12 | 6 | 0 | 0
Health and Saftey
6 | That there is a failure to meet statutory and legislative health and safety as well as safeguarding requirements. | 2 | 5 | 3 | 15 | 15 | 0 | 5 | 2 | 15 | 10 | 5 | Head of Estates | Health and Saftey | 15 | 15 | 0 | -5
Legal/Compliance
4 | That there is a breach of legislation and associated regulations (incl. GDPR) | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of MIS | Legal/Compliance | 6 | 4 | 0 | 0
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 3 | 0 | Executive Team | Legal/Compliance | 9 | 3 | 0 | 0
15 | That the College is not on track to meet the Scottish Government net zero targets. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | VP for Finance, Estates and Sustainability | Legal/Compliance | 9 | 6 | 0 | 0
Learning Teaching and Student Experience - LTSE (Operations)
9 | That there is a failure to achieve high standards of learning and teaching. | 1,2 | 4 | 3 | 12 | 12 | 0 | 4 | 1 | 4 | 4 | 0 | VP for Learning & Teaching | LTSE | 12 | 4 | 0 | 0
12 | That the College cannot provide a robust learner experience supporting them onto their final destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 4 | 1 | 4 | 4 | 0 | VP for Learning & Teaching | LTSE | 8 | 4 | 0 | 0
People | [17 empty] | 0
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 4 | 16 | 16 | 0 | 4 | 2 | 8 | 8 | 0 | Head of HR | People | 16 | 8 | 0 | 0
Property
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 3 | 5 | 15 | 15 | 0 | 3 | 4 | 12 | 12 | 0 | Head of MIS | Property | 15 | 12 | 0 | 0
Strategy
14 | That there is a reputational risk to the College. | 3 | 4 | 3 | 12 | 12 | 0 | 3 | 3 | 9 | 9 | 0 | Principal | Strategy | 12 | 9 | 0 | 0
College Strategic Objectives: | [7 empty] | Risk Key | Low | 1-3
1 | Student Experience | [7 empty] | Medium | 4-9
2 | Culture and People Development | [7 empty] | High | 10-19
3 | Growth and Innovation | [7 empty] | Very High | 20-25
4 | Sustainability

## Aug 24 SLC Summary (hidden)
Strategic Risk Register |  |  | Dated reviewed by Risk Management Group |  |  |  | 16/01/2024 | [5 empty] | RSRMG
Summary Schedule |  |  | Dated reviewed by SLT |  |  |  | 22/01/2024 | [5 empty] | 2024-01-01
|  |  | Next date of review | [9 empty] | Agenda Item ***
Risk No. | Description | Link to College Strategic Objectives | Impact Rating (1-4) | Probability Rating (1-4) | Risk Score | Previous submission risk score | Movement since last submission | Post-mitigation impact | Post-mitigation probability | Post-mitigation score | Previous submission mitigation score | Movement since last submission | Risk Owner
1 | That the College cannot maintain financial stability | 3 | 4 | 4 | 16 | 16 | 0 | 4 | 4 | 16 | 16 | 0 | VP for Finance, Estates and Sustainability
2 | That there is a failure of financial controls | 3 | 4 | 2 | 8 | 8 | 0 | 3 | 4 | 12 | 9 | 3 | VP for Finance, Estates and Sustainability
3 | That there is failure to meet Credit target and /or failure to retain major public and private contracts. | 1,3 | 4 | 3 | 12 | 12 | 0 | 3 | 2 | 6 | 3 | 3 | VP for Learning & Teaching
4 | That there is a breach of legislation and associated regulations (incl. GDPR) | 2,3 | 2 | 3 | 6 | 6 | 0 | 2 | 2 | 4 | 4 | 0 | Head of IT
5 | That there are insufficient funds for capital project and maintenance requirements | 1,3 | 4 | 2 | 8 | 8 | 0 | 3 | 4 | 12 | 9 | 3 | VP for Finance, Estates and Sustainability
6 | That there is a failure to meet statutory and legislative health and safety as well as safeguarding requirements. | 2 | 3 | 3 | 9 | 9 | 0 | 3 | 2 | 6 | 6 | 0 | Head of Estates / Head of IT
7 | That there is business interruption due to major disaster, IT failure etc | 3 | 4 | 2 | 8 | 8 | 0 | 3 | 2 | 6 | 6 | 0 | Head of IT
8 | That there is a theft of, or damage to, Management Information System (incl. cyber-crime) | 2,3 | 3 | 2 | 6 | 6 | 0 | 3 | 1 | 3 | 3 | 0 | Head of IT
9 | That there is a failure to achieve high standards of learning and teaching. | 1,2 | 4 | 2 | 8 | 8 | 0 | 2 | 2 | 4 | 4 | 0 | VP for Learning & Teaching
10 | That there is a failure to provide an engaging and effective employee journey. | 1,2 | 4 | 2 | 8 | 8 | 0 | 3 | 1 | 3 | 6 | -3 | Head of HR
11 | That there is a failure to safeguard the health and wellbeing of staff and students. | 1,2,3 | 3 | 3 | 9 | 9 | 0 | 3 | 1 | 3 | 6 | -3 | VP for Learning & Teaching
12 | That the College cannot provide a robust learner experience supporting them onto their final destinations. | 1,2 | 4 | 2 | 8 | 8 | 0 | 3 | 4 | 12 | 9 | 3 | VP for Learning & Teaching
13 | That there is a failure of Corporate Governance arrangements | 2,3 | 4 | 2 | 8 | 8 | 0 | 3 | 2 | 6 | 6 | 0 | Governance Professional
14 | That there is a reputational risk to the College. | 3 | 4 | 4 | 16 | 16 | 0 | 3 | 4 | 12 | 12 | 0 | Principal
15 | That the College is not on track to meet the Scottish Government net zero targets. | 3 | 3 | 3 | 9 | 9 | 0 | 3 | 3 | 9 | 6 | 3 | VP for Finance, Estates and Sustainability
College Strategic Objectives: | [7 empty] | Risk Key | Low | 2024-01-04
1 | Successful students | [7 empty] | Medium | 2024-05-11
2 | Highest quality education and support | [7 empty] | High | 2024-12-16
3 | Sustainable behaviours